## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 4882/ND | 23/11/2022 | 23/11/2022 | Resource Division | 73.95 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. |  |  | VCH/000334/2022-2023 | 43/PFMS | 09/06/2022 | 09/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.93 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works etc. rejuvenation to Accommodate FHTC at Pump House No.I and II under Anulia WS Scheme, Block Ranaghat 1, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-10) |  | Junior Engineer | ORD/000891/2022-2023 | 159/EMD | 06/01/2023 | 05/02/2023 | KARTICK BAL | 27.77 | 24.21 | 87.21 | 40
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 4331/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.06 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 2123/ND | 16/05/2023 | 16/05/2023 | Resource Division | 77.07 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Surging of 01(One) nos. 150 x 100mm dia tube well at second tube well site of Anulia water supply scheme under Ranaghat Sub-Division Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000303/2023-2024 | 931/RSD | 14/09/2023 | 21/09/2023 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.55 | 0.55 | 100 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Estimate for Surging of 01(One) nos. 150 x 100mm dia tube well Head works site of Anulia water supply scheme under Ranaghat Sub-Division Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000304/2023-2024 | 932/RSD | 14/09/2023 | 21/09/2023 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 0.55 | 0.49 | 89.31 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000110/2022-2023 | 3528/ND | 05/08/2022 | 03/11/2022 | M/S NANDY ENTERPRISE | 475.17 | 309.5 | 65.13 | 95
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Anulia under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000802/2024-2025 | 1410/RSD | 19/11/2024 | 03/01/2025 | SURJA ENTERPRISE | 2.15 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Anulia to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division, PHE Dte. | SM/10716 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 758.16 | 334.76 | 44.15