## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Proposed Augmentation of Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 1 No. Pump House at proposed Head Work site & Tube Well site, Construction of R.C.C. Elevated Reservoir of 750 Cum capacity (including pile foundation), and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Bhimpur (Phase-II) to accommodate FHTC within Krishnagar-I Block under Krishnanagar Sub-division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000151/2023-2024 | 3218/ND | 26/07/2023 | 26/07/2025 | SINGHA ROY & CO. | 339.59 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 01/07/2025 | C.M.S. ENGINEERING CONCERN. | 70.97 | 4.44 | 6.26 | 12
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
4 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bhimpur (Phase-II) W/S Scheme (TW-I) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 1654/CDD | 17/10/2023 | 16/11/2023 | MENAKA ENTERPRISE | 18.88 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 84/ND | 05/01/2023 | 05/01/2023 | Resource Division | 106.78 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 136 m3/hr at Bhimpur Water Supply Scheme within Krishnagar-I Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000194/2024-2025 | 6221/ND | 23/09/2024 | 22/03/2025 | GHOSH ENTERPRISE | 315.76 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Repair & Renovation of Pump House, Boundary wall and allied works at 1st and 2nd Pump House at Bhimpur Water Supply Scheme within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000476/2023-2024 | 154/ND | 09/01/2024 | 01/01/2025 | SUNIL KUMAR DATTA | 12.15 | 0 | 0 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 260/ND | 11/01/2024 | 11/01/2024 | Resource Division | 16.52 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte. | SM/10726 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 1074.58 | 5.84 | 0.54