## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Teorkhali W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 12) | Assistant Engineer |  | ORD/000351/2021-2022 | 915/KSD | 29/11/2021 | 14/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.39 | 3.38 | 99.82 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Fencing for Land at Chapra Bangaljhi and Teorkhali Water supply scheme at new 3rd Tube Well site under Krishnagar Sub-Division PHED. | Assistant Engineer |  | ORD/000532/2022-2023 | 219/KSD | 03/03/2023 | 18/03/2023 | SANJIB DEY | 0.45 | 0.22 | 49.98 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer |  | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 17/12/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2022-2023 | 109/ND | 05/01/2023 | 05/01/2023 | Resource Division | 31.18 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 104 m3/hr at Teorkhali Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000781/2023-2024 | 1895/ND | 15/03/2024 | 11/09/2024 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 268.24 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer 3 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 28/12/2024 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Sinking of 1 no. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method and construction of pump house (3.6 mtr. x 3.0 mtr.) and boundary wall at 3rd tube well site for Teorkhali water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE,Dte. (Sm/10728) | Assistant Engineer | Junior Engineer 4 | ORD/000032/2023-2024 | 2100/ND | 15/05/2023 | 13/08/2023 | MONDAL ENTERPRISE | 29.84 | 25.7 | 86.13 | 75
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 625/ND | 30/01/2024 | 30/01/2024 | Resource Division | 9.92 | 0 | 0 | 0
10 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | New service connection at Ph-3 of Teorkhali water supply scheme, Block-Nabadwip, Dist-Nadia |  |  | BILL/00728/2024-2025 | BP-51-24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL SWARUPGANJ C.C.C. | 7.71 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Name of Work: Laying of Distribution System including specials & valves, pipe supporting structure all complete, proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of R.C.C. Elevated Reservoir of 600 Cum capacity(including pile foundation) and Soil investigation for construction of one No. 600 Cum OHR at Tiorkhali to accommodate FHTC within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000200/2023-2024 | 3510/ND | 10/08/2023 | 11/08/2026 | MONDAL ENTERPRISE | 579.26 | 331.41 | 57.21 | 35
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Repair & Renovation of Pump House, Boundary wall, Store Room and allied works at 1st and 2nd Pump House at Tiorkhali Water Supply Scheme within Nabadwip block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000501/2023-2024 | 6183/ND | 27/12/2023 | 25/04/2025 | BIPLAB GUHA | 17.98 | 10.44 | 58.09 | 35
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte. | SM/10728 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-III under TIORKHALI ground water based water supply scheme under Block_ KRISHNANAGAR, Dist. - Nadia under EMD, PHE Dte. [SM/10728] | Assistant Engineer | Junior Engineer | ORD/000336/2024-2025 | 2151/EMD | 30/08/2024 | 28/02/2025 | SWAPAN ENTERPRISE | 13.8 | 0 | 0 | 95
Total | [13 empty] | 1064.75 | 372.56 | 34.99