## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-10B W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000407/2021-2022 | 321/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 2.44 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 2313/ND | 29/05/2023 | 29/05/2023 | Resource Division | 5.45 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IV, V & XB) W/S Scheme, Block-Karimpur I , Dist. - Nadia. NIET NO. - 33 OF EE/EMD OF 2022-23 (SL. NO. - 03) | Assistant Engineer | Junior Engineer | ORD/001926/2022-2023 | 1198/EMD | 22/03/2023 | 01/05/2025 | AVINABA ENGINEERING CONCERN | 62.41 | 0 | 0 | 80
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Construction of barbed wire fencing with concrete pillars at Hatisala Karimpur-Jalangi Zone-X(B) water supply scheme (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM |  | Junior Engineer 1,Junior Engineer 2 | ORD/000730/2023-2024 | 1120/TSD | 21/02/2024 | 28/02/2024 | NIVEDITA CONSTRUCTION | 1.46 | 0 | 0 | 100
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi Zone-X,B (Hatisala) PH-II under EMSD-III,Nadia |  |  | BILL/02239/2024-2025 | BP-179 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 7.19 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement at H.W Site and consruction of Boundary wall at Head Work Site At Karimpur Jalangi Zone- X(B) Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000760/2023-2024 | 1633/ND | 07/03/2024 | 25/02/2026 | M/S BAPI ENTERPRISE | 24.15 | 0 | 0 | 80
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Jone-XB to accommodate FHTC Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000342/2022-2023 | 242/ND | 13/01/2023 | 10/04/2025 | CHOWDHURY & CO. | 79.52 | 0 | 0 | 90
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/10737 | Augmentation | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Karimpur Jalangi PWSS Zone-X(B) Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000691/2023-2024 | 1226/ND | 22/02/2024 | 17/01/2025 | MANISHIKA CONSTRUCTION | 17.38 | 0 | 0 | 100
Total | [13 empty] | 199.99 | 0 | 0