## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - A | Assistant Engineer |  | ORD/000316/2021-2022 | 1189/PH | 03/12/2021 | 13/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.82 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 3894/ND | 08/09/2022 | 08/09/2022 | Resource Division | 82.06 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 4328/ND | 29/09/2022 | 29/09/2022 | Resource Division | 39.36 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 3375/ND | 04/08/2023 | 04/08/2023 | Resource Division | 3.11 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Providing last mile connectivity including FHTC to cover Shyamnagar and Berij village in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Subarna Bihar ZONE-I in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000812/2023-2024 | 474/KlySD-II | 07/03/2024 | 21/04/2024 | M/S BISWAS ENTERPRISE | 2.15 | 1.75 | 81.25 | 82
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Laying of Distribution System including specials, valves all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Subarnabehar Zone-I to accommodate FHTC within Krishnagar-I Block under RWS Nadia Sub-Divn under Nadia Divn, PHE Dte. (SM/11506) | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000180/2022-2023 | 4383/ND | 13/10/2022 | 19/12/2024 | MONDAL ENTERPRISE | 493.02 | 462.47 | 93.81 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 231 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Subarnabihar Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000026/2023-2024 | 1784/ND | 20/04/2023 | 19/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 222.99 | 0 | 0 | 65
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-I under Subarnabehar Zone-I ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2024-2025 | 1311/EMD | 09/05/2024 | 08/06/2024 | DAS ENTERPRISE (BARANAGAR) | 12.77 | 11.82 | 92.54 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Repair and renovation works of R.C.C. Elevated Existing Over Head Reservoir of capacity 1000 Cu.M for Subarnabehar Zone-I Water Supply Scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000710/2023-2024 | 1300/ND | 23/02/2024 | 23/04/2024 | S.S.CONSULTANCY & CONSTRUCTION | 16.66 | 9.95 | 59.73 | 96
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Special repair and renovation of Existing Boundary Wall at Head work site of Subarnabihar Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000711/2023-2024 | 1301/ND | 23/02/2024 | 08/04/2024 | ABHAYANANDA ENTERPRISE | 6.81 | 6.44 | 94.63 | 98
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Special repair and renovation of pump house and allied works for Head work site (Existing) at Subarnabihar Zone I water supply scheme in Nadia District under Nadia Division PHE. Dte | Assistant Engineer | Junior Engineer 2 | ORD/000791/2023-2024 | 472/KlySD-II | 07/03/2024 | 06/04/2024 | RAIHANA ENTERPRISE | 1 | 1 | 99.75 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Special repair and renovation of Existing Boundary Wall " for 2nd ,3rd, 4th & 5th Tube Well site at Subarnabihar Zone I water supply scheme in Nadia District under Kalyani Sub-Divn-II, under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000786/2023-2024 | 1903/ND | 15/03/2024 | 29/04/2024 | CONSTRUCTURE | 5.07 | 4.79 | 94.47 | 95
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Special repair and renovation of pump house and allied works for 2nd ,3rd, 4th & 5th Tube Well site(Existing) at Subarnabihar Zone I water supply scheme in Nadia Distric under Nadia Division PHE. Dte | Assistant Engineer | Junior Engineer 2 | ORD/000839/2023-2024 | 475/KlySD-II | 11/03/2024 | 10/05/2024 | DAFADAR ENTERPRISE | 1.61 | 1.59 | 98.6 | 98
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Laying of distribution pipeline along with FHTC additionally to cover the remaining portion of Subarnabihar Zone-I Water Supply Scheme withih Krishnagar ¿I Block under Kalyani Sub-Division-II under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000035/2024-2025 | 3451/ND | 20/06/2024 | 15/06/2025 | BUDDHADEV MONDAL | 65.26 | 9.87 | 15.12 | 75
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Installation of Manifold, laying of dedicated pipeline and other necessary allied works for Subarnabihar Zone-I Water Supply Scheme in Krishnagar-I Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000048/2025-2026 | 2115/ND | 02/05/2025 | 28/12/2025 | BUDDHADEV MONDAL | 88.11 | 0 | 0 | 35
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Laying of delivery main for Usidpur and Subarnabihar (P) Mouza under Krishnagar-I Block in Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000051/2025-2026 | 2288/ND | 19/05/2025 | 18/07/2025 | M/S GHOSH CONSTRUCTION | 63.02 | 0 | 0 | 99
17 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Construction of Boundary wall to protect the aditional space of Subarnabihar Zone I water Supply Scheme under nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000108/2025-2026 | 2849/ND | 18/06/2025 | 17/08/2025 | M/S K.P.PAL | 6.48 | 0 | 0 | 0
18 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-I to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte. | SM/11506 | Augmentation | Installation of Reclaim Filter for renovation of AIRP ( Gravity type) of capacity 231 Cu.m/hr at head work site at SUBARNABIHAR ZONE I PWSS under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000424/2024-2025 | 7166/ND | 10/12/2024 | 08/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 40.55 | 0 | 0 | 98
Total | [13 empty] | 1154.84 | 514.5 | 44.55