## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - B | Assistant Engineer |  | ORD/000317/2021-2022 | 1190/PH | 03/12/2021 | 13/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.69 | 1.68 | 99.95 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | continuation order of Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar zone - II W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000757/2021-2022 | 1198/PH | 07/12/2021 | 14/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.6 | 1.6 | 100 | 100
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Supplying, Laying, Fitting & Fixing of Distribution System including all type of specials, valves, pipes all complete, Proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction & Soil investigation of 350 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (With Pile Foundation), Pipe Connection and Cost of Pipes, Specials, Construction of 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement, HW Site & 1 (One) No. Pump House (4.88m X 3.66m) Including Sanitary Arrangement Tw Site-2, Construction of Boundary Wall, Service Road (60 Mtr. Length X 3 Mtr. Width) at Head Work Site & Service Road (15 Mtr. Length X 2 Mtr. Width) at Tube Well Site for Subarna Behar ZONE-II in Krishnagar-I Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000163/2023-2024 | 3194/ND | 26/07/2023 | 26/07/2027 | M/S GHOSH CONSTRUCTION, SUKUL ROAD, P.O-KRISHNAGAR, DIST.NADIA, PIN-741101, WB | 440.53 | 0 | 0 | 5
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
5 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Subarnabihar W/S Scheme (Z-II, TW-I & II) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000251/2023-2024 | 1229/CDD | 04/09/2023 | 01/05/2026 | SUNRISE ENGINEERING CORPORATION | 37.71 | 0 | 0 | 50
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000191/2022-2023 | 241/ND | 13/01/2023 | 13/01/2023 | Resource Division | 85.16 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 65 m3/hr at Subarnabihar Zone-II Water Supply Scheme including 3 Months Trial Run & 3 Years O&M within Krishnanagar-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000723/2023-2024 | 1354/ND | 27/02/2024 | 25/08/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 204.6 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly Head Work Site under SUBARNA BEHAR (ZONE-II) W/S Scheme in KRISHNAGAR - 1 Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3005020477) |  |  | BILL/02151/2024-2025 | BP-170-24-25 | 05/12/2024 | 05/12/2024 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 6.39 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte | SM/11507 | Augmentation | Laying of additional pipeline as per the revised drawing for augmentation of Subarnabihar Zone-II Water Supply Scheme in Krishnagar-I Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000050/2025-2026 | 2287/ND | 19/05/2025 | 15/11/2025 | M/S GHOSH CONSTRUCTION | 91.02 | 0 | 0 | 0
Total | [13 empty] | 965.67 | 6.08 | 0.63