## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2022-2023 | 158/ND | 06/01/2023 | 06/01/2023 | Resource Division | 22.47 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 2306/ND | 29/05/2023 | 29/05/2023 | Resource Division | 26.43 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Plumbing & allied Works for toilet & guard room at Habibpur under Ranaghat Sub-Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000152/2024-2025 | 795(A)RSD | 02/08/2024 | 22/08/2024 | SKYLINE CONSTRUCTION | 0.95 | 0.95 | 99.75 | 100
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Guard Room Repair at Habibpur water supply scheme under Ranaghat Sub-Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000150/2024-2025 | 794/RSD | 02/08/2024 | 22/08/2024 | SKYLINE CONSTRUCTION | 0.94 | 0.93 | 99.79 | 100
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Toilet construction of Guard Room of Habibpur water supply scheme under Ranaghat Sub-Division under Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000151/2024-2025 | 795/RSD | 02/08/2024 | 22/08/2024 | SKYLINE CONSTRUCTION | 0.82 | 0.78 | 94.38 | 100
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | "Restoration work arising out of damage of Hard Shoulder for Laying of UPVC Pipe Line by Nadia Division, PHED" under Nadia Highway Division No-II in the District of Nadia during the year 2023-24 Pt.-II "NH Tarapur to Balagarhghat Road from Ch 0.00 Km to Ch1.80 Km". |  |  | BILL/00394/2024-2025 | 228/PFMS | 11/09/2024 | 11/09/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-II, P.W. (ROADS) DIRECTORATE | 6 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | Assistant Engineer | Junior Engineer 2 | ORD/000248/2022-2023 | 4990/ND | 30/11/2022 | 04/04/2025 | M/S GHOSH CONSTRUCTION | 335.48 | 265.28 | 79.07 | 100
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Construction of Boundary wall at Habibpur W/S Scheme under Ranaghat Sub-Division, Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000136/2024-2025 | 875/RSD | 20/08/2024 | 20/09/2024 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 3.78 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Habibpur under Ranaghat Sub-Division under Nadia Division PHE Dte. |  | Junior Engineer 2 | ORD/000674/2024-2025 | 1416/RSD | 19/11/2024 | 03/01/2025 | SARKAR ENTERPRISE | 2.16 | 0 | 0 | 80
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Habibpur under piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000205/2024-2025 | 1142/RSD | 11/09/2024 | 26/10/2024 | PURBA SERVICES | 1.9 | 0.46 | 24.47 | 100
11 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED HABIBPUR PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT- I BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11508 | Augmentation | Balanced UPVC pipe line for Providing Functional Household Tap Connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Habibpur to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000035/2025-2026 | 2156/ND | 06/05/2025 | 04/08/2025 | M/S DIPAK ENTERPRISE | 164.59 | 0 | 0 | 0
Total | [13 empty] | 565.51 | 268.4 | 47.46