## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11509 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1884/ND | 26/04/2023 | 26/04/2023 | Resource Division | 44.93 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11509 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 2312/ND | 29/05/2023 | 29/05/2023 | Resource Division | 42.04 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11509 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 28/ND | 03/01/2024 | 03/01/2024 | Resource Division | 32.2 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11509 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-I to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | Assistant Engineer | Junior Engineer 2 | ORD/000317/2022-2023 | 16/ND | 03/01/2023 | 16/03/2026 | KINGS & CO. | 415.48 | 285.42 | 68.7 | 85
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11509 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KAMGACHI PWSS PART-II TO ACCOMMODATE FHTC IN RANAGHAT-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11509 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Kamgachi Zone-II to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. (PART-II) | Assistant Engineer | Junior Engineer 2 | ORD/000300/2022-2023 | 5354/ND | 22/12/2022 | 06/12/2025 | JOY HIND TUBEWELL'S | 340.71 | 268.53 | 78.81 | 100
Total | [13 empty] | 972.34 | 553.95 | 56.97