## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000436/2021-2022 | 1056/RSD | 02/12/2021 | 01/01/2022 | RADIANT | 3.29 | 2.97 | 90.26 | 100
2 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Providlng drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utillsing Departmental Machineries for Badkulla W/S Scheme (Z-11,1/W-l), Hanskhali Block under Nadia District, CentralDrilling Division, P.H.E. Dte (znd Call). |  |  | ORD/000097/2023-2024 | 1052/CDD | 16/08/2023 | 15/09/2023 | MENAKA ENTERPRISE | 18.6 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1881/ND | 26/04/2023 | 26/04/2023 | Resource Division | 100.61 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under BADKULLA Z-II WS Scheme, Block- Hanskhali , Dist. - Nadia. |  |  | ORD/001124/2023-2024 | 4712/EMD | 04/08/2023 | 03/09/2023 | KASHINATH PAL & CO. | 9.79 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Construction of 125.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Badkulla -II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHED. | Assistant Engineer |  | ORD/000104/2024-2025 | 4280/ND | 05/08/2024 | 01/02/2025 | MANGES INDUSTRIAL CORPORATION | 303.09 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Badkulla Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000222/2024-2025 | 1186/RSD | 25/09/2024 | 09/12/2024 | AVIRUP CONSTRUCTION | 4.46 | 0 | 0 | 90
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 7557/ND | 27/12/2024 | 27/12/2024 | Resource Division | 8.68 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000018/2025-2026 | 1804/ND | 22/04/2025 | 19/10/2025 | APURBA MANDAL | 64.83 | 0 | 0 | 90
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000084/2025-2026 | 2523/ND | 29/05/2025 | 29/05/2026 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Badkulla Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000175/2024-2025 | 1138/RSD | 11/09/2024 | 26/10/2024 | SUPRIYA DEY | 1.89 | 1.64 | 87.12 | 100
Total | [13 empty] | 776.63 | 7.41 | 0.95