## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000436/2021-2022 | 1056/RSD | 02/12/2021 | 01/01/2022 | RADIANT | 3.29 | 0 | 0 | 100
2 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Providlng drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utillsing Departmental Machineries for Badkulla W/S Scheme (Z-11,1/W-l), Hanskhali Block under Nadia District, CentralDrilling Division, P.H.E. Dte (znd Call). |  |  | ORD/000097/2023-2024 | 1052/CDD | 16/08/2023 | 15/09/2023 | MENAKA ENTERPRISE | 18.6 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1881/ND | 26/04/2023 | 26/04/2023 | Resource Division | 100.61 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Supply, Delivery and Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under BADKULLA Z-II WS Scheme, Block- Hanskhali , Dist. - Nadia. |  |  | ORD/001124/2023-2024 | 4712/EMD | 04/08/2023 | 03/09/2023 | KASHINATH PAL & CO. | 9.79 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Construction of 125.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Badkulla -II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHED. | Assistant Engineer |  | ORD/000104/2024-2025 | 4280/ND | 05/08/2024 | 01/02/2025 | MANGES INDUSTRIAL CORPORATION | 303.09 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Badkulla Zone-II Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000222/2024-2025 | 1186/RSD | 25/09/2024 | 09/12/2024 | AVIRUP CONSTRUCTION | 4.46 | 0 | 0 | 90
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 7557/ND | 27/12/2024 | 27/12/2024 | Resource Division | 8.68 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Badkulla Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering | Assistant Engineer | Junior Engineer 1 | ORD/000149/2023-2024 | 3216/ND | 26/07/2023 | 26/07/2024 | SATYABRATA CHAKRABORTY | 371.16 | 0 | 0 | 50
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000018/2025-2026 | 1804/ND | 22/04/2025 | 19/10/2025 | APURBA MANDAL | 64.83 | 0 | 0 | 90
11 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11510 | Augmentation | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000084/2025-2026 | 2523/ND | 29/05/2025 | 29/05/2026 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0 | 0
Total | [13 empty] | 1145.91 | 0 | 0