## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Topla W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000389/2021-2022 | 305/TSD | 24/11/2021 | 24/12/2021 | HORIZEN | 3.19 | 2.81 | 88.05 | 100
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Rising main from First Tube Well, 2nd Tube well with 3rd tube well and Inter-Connection in between Tube wells and OHR including specials and valves and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Topla to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. (SM/11511) | Assistant Engineer | Junior Engineer 1 | ORD/000179/2022-2023 | 4387/ND | 13/10/2022 | 11/01/2023 | M/S DIPAK ENTERPRISE | 314.83 | 229.19 | 72.8 | 75
3 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR TOPLA W/S SCH, KARIMPUR-II BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000382/2022-2023 | 1197/CDD | 11/11/2022 | 11/12/2022 | ASHUTOSH DAS & CO | 10.19 | 7.45 | 73.1 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 5102/ND | 08/12/2022 | 08/12/2022 | Resource Division | 45.9 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 4317/ND | 29/09/2022 | 29/09/2022 | Resource Division | 18.41 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAHISUNRA W/S Scheme, Block-NABADWIP, PALASIPARA W/S Scheme, Block-Tehatta-II AND TOPLA W/S Scheme, Block-Karimpur-II Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No. - 05) | Assistant Engineer | Junior Engineer | ORD/001011/2022-2023 | 499/EMD | 24/01/2023 | 23/02/2023 | WEST BENGAL ENGINEERING CO. | 90.14 | 29.92 | 33.2 | 15
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Renovation of AIRP (Pressure Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Topla PWSS under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000213/2023-2024 | 3584/ND | 14/08/2023 | 12/11/2023 | APURBA MANDAL | 68.26 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Habibpur(PART-II) ii) Madhugari (Phase-II) iii) Krishnaganj (Phase-I) iv) Naserkuli (Zone-I) v) Topla | Assistant Engineer | Junior Engineer 2 | ORD/000439/2022-2023 | 245/ Kly SD-I | 27/02/2023 | 27/08/2023 | HORIZEN | 4.96 | 4.96 | 100 | 100
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 2288/ND | 29/05/2023 | 29/05/2023 | Resource Division | 18.41 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement At Tube well No-3 Site and construction of Boundary wall at 3rd Tube Well Site At Topla Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000761/2023-2024 | 1634/ND | 07/03/2024 | 25/02/2026 | BISWAS ENTERPRISE | 11.78 | 0 | 0 | 80
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 3rd Tube well Site Topla PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000683/2024-2025 | 7481/ND | 23/12/2024 | 22/01/2025 | ZEST INFRACON | 17.55 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Topla water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000403/2024-2025 | 7126/ND | 09/12/2024 | 05/09/2025 | MONDAL ENTERPRISE | 34.35 | 0 | 0 | 80
13 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Topla Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Topla at Karimpur-II Block by Augmentation of Ground Water based PWSS for Topla Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000098/2025-2026 | 2263/ND | 15/05/2025 | 14/07/2025 | SOURAV & CO | 23.57 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Quotation for new service connection and security deposit for Topla W/S scheme. |  |  | BILL/02436/2024-2025 | BP-208 | 09/01/2025 | 09/01/2025 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 4.54 | 0 | 0 | 0
15 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA | SM/11511 | Augmentation | Supplementary quotation for service connection and security deposit for Topla PH-III |  |  | BILL/00800/2026-2027 |  | 23/06/2026 | 23/06/2026 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 5.85 | 0 | 0 | 0
Total | [13 empty] | 671.93 | 274.32 | 40.83