## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-9B W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000404/2021-2022 | 319/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 2.42 | 2.42 | 100 | 100
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI (Z-IX B) W/S Scheme, Block-Karimpur II , Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No. 05) |  |  | ORD/001924/2022-2023 | 1180/EMD | 21/03/2023 | 20/04/2023 | MA ANNAPURNA ENTERPRISE | 12.87 | 11 | 85.41 | 10
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under Karimpur jalangi (Zone-IX,A & B) W/S Scheme, Block-Tehatta-II, Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 19) |  |  | ORD/002779/2022-2023 | 419EMD | 20/01/2023 | 19/02/2023 | SINHA ELECTRICALS | 14.88 | 1.34 | 9.01 | 85
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1902/ND | 27/04/2023 | 27/04/2023 | Resource Division | 18.83 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Sinking of 01 no Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Karimpur Jalangi PWSS Zone-IX(B) Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000663/2023-2024 | 1098/ND | 19/02/2024 | 15/11/2024 | BUDDHADEV MONDAL | 17.38 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Construction of barbed wire fencing with concrete pillars at Karimpur-Jalangi Zone-IX(B). water supply scheme (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . |  | Junior Engineer 1,Junior Engineer 2 | ORD/000731/2023-2024 | 1121/TSD | 21/02/2024 | 28/02/2024 | NIVEDITA CONSTRUCTION | 1.51 | 1.35 | 89.73 | 100
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction Of 200 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (without pile foundation), Pipe Connection and cost of Pipes, Specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of cum. O.H.R. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IXB to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000446/2022-2023 | 965/ND | 09/03/2023 | 03/01/2027 | SHYAMAL SHIL, PALLISREE, P.O.KRISHNAGAR, DIST- NADIA,PIN-741101 | 175.66 | 42.49 | 24.19 | 45
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement and Construction of Boundary wall at Head Work Site at Karimpur - Jalangi (IX-B )Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000759/2023-2024 | 1632/ND | 07/03/2024 | 26/07/2025 | MONDAL ENTERPRISE | 23.85 | 9.92 | 41.59 | 15
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 26.25 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-IX B to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000340/2024-2025 | 7105/ND | 06/12/2024 | 01/12/2025 | JOY HIND TUBEWELL'S | 151.86 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11512 | Augmentation | Repairing and renovation works of Pump House and allied works of ground based piped water supply scheme for Karimpur Jalangi Zone-IX(B) and Karimpur Jalangi Zone-X(B)water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000394/2024-2025 | 7121/ND | 09/12/2024 | 09/03/2025 | PURNIMA ELECTRICS & DECORATORS | 9.07 | 0 | 0 | 100
Total | [13 empty] | 428.33 | 68.52 | 16