## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Karimpur-Jalangi Z-6 (I&II) W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000400/2021-2022 | 315/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 4.54 | 4.54 | 100 | 100
2 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300 mm x 200 mm x 250Mtrs. Depth) by utilising Departmental machineries for Karimpur jalangi W/S Scheme (Z-VI TW-I & II) Karimpur-I Block under Nadia District CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000040/2023-2024 | 98/CDD | 17/04/2023 | 17/05/2023 | SUNRISE ENGINEERING CORPORATION | 37.28 | 27.4 | 73.5 | 100
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1901/ND | 27/04/2023 | 27/04/2023 | Resource Division | 60.25 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under KARIMPUR JALANGI(Z-6) W/S Scheme, Block- Karimpur I, & KAMALPUR (Z-II) W/S Scheme, Block-Ranaghat II, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 04) |  |  | ORD/001925/2022-2023 | 1197/EMD | 22/03/2023 | 21/04/2023 | P.K. ENGINEERING | 48.95 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Quotation charges for new service connection and security deposit at Karimpur Jalangi (Zone-VI,B) PH-I under EMSD-III,Nadia |  |  | BILL/02244/2024-2025 | BP-180 | 13/12/2024 | 13/12/2024 | WBSEDCL KARIMPUR CCC | 10.19 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Quotation for new service connection and security deposit for Karimpur Jalangi Zone- 6, Part- B (H/W site) |  |  | BILL/02314/2024-2025 | BP-196-24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL KARIMPUR CCC | 15.95 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI Part A & Karimpur Jalangi Zone-VI Part B to accommodate FHTC and Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of 200 CUM OHR for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI Part B for Ground Based Water Supply Scheme at Karimpur Jalangi Zone-VI (A&B) under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000091/2023-2024 | 3028/ND | 14/07/2023 | 14/07/2024 | BALAJI UDDYOG, 153/2B, A.P.C. ROAD, 1ST FLOOR, KOLKATA- 700006. | 520.9 | 311.8 | 59.86 | 55
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Karimpur Jalangi Zone-VI water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000312/2024-2025 | 6839/ND | 12/11/2024 | 05/02/2026 | MS MAA BHABANI ENTERPRISE | 31.29 | 0 | 0 | 50
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 07/01/2026 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 40
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11513 | Augmentation | Construction Of Pump House (5.4m X 3.6m) & (3.6m X 3.0m) Including Sanitary Arrangement At Head Work Site & 2nd tube well Site and construction of Boundary wall at Head works site & 2nd tube well site of Karimpur Jalangi Zone- VI(B) Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000757/2023-2024 | 1631/ND | 07/03/2024 | 03/03/2025 | N.H. ENTERPRISE | 47.26 | 16.99 | 35.95 | 65
Total | [13 empty] | 855.8 | 360.73 | 42.15