## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of one no of Lab attendant and one no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. WEF 01/01/2022 to 31/05/2022 (Five months) | Assistant Engineer |  | ORD/000512/2021-2022 | 648/Kly SD-I | 27/12/2021 | 27/05/2022 | M/S S.K. ENTERPRISE | 0.94 | 0.88 | 93.1 | 0
2 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.01.2022 to 31.12.2022 (One Year). | Assistant Engineer |  | ORD/000467/2021-2022 | 7541/ND | 30/12/2021 | 30/12/2022 | CLIFFORD FACILITY SERVICES PVT. LTD | 16.94 | 16.67 | 98.39 | 100
3 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Maintenance of Nadia District Laboratory under Kalyani Sub Division-I under Nadia Division PHE Dte. w.e.f 01/09/2021 to 31/08/2022 | Assistant Engineer |  | ORD/000193/2021-2022 | 328 / KlY SD-I | 31/08/2021 | 31/08/2022 | MANISHIKA CONSTRUCTION | 1.57 | 1.57 | 99.7 | 0
4 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Engagement of 01 no of Chemist /Analyst for operation and maintenance of physicoChemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/09/2022 to 28/02/2023 (Six months) | Assistant Engineer |  | ORD/000138/2022-2023 | 787/Kly SD-I | 01/09/2022 | 01/03/2023 | JOYDEV JANA | 0.99 | 0.99 | 100 | 0
5 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/09/2022 to 28/02/2023 (Six months) | Assistant Engineer |  | ORD/000139/2022-2023 | 788/Kly SD-I | 01/09/2022 | 01/03/2023 | SUCHITRA GHOSH | 0.46 | 0.46 | 100 | 0
6 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/09/2022 to 28/02/2023 (Six months) | Assistant Engineer |  | ORD/000140/2022-2023 | 789/Kly SD-I | 01/09/2022 | 01/03/2023 | GOUTAM DAM | 0.99 | 0.99 | 100 | 0
7 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.01.2023 to 28.02.2023 (Two Month). | Assistant Engineer |  | ORD/000314/2022-2023 | 5454/ND | 29/12/2022 | 28/02/2023 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.73 | 100 | 0
8 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2022 to 31/08/2022 (Three months) | Assistant Engineer |  | ORD/000027/2022-2023 | 452/Kly SD-I | 30/05/2022 | 30/08/2022 | JOYDEV JANA | 0.5 | 0.17 | 33.33 | 0
9 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2022 to 31/08/2022 | Assistant Engineer |  | ORD/000028/2022-2023 | 453/Kly SD-I | 30/05/2022 | 30/08/2022 | GOUTAM DAM | 0.5 | 0.17 | 33.33 | 0
10 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/09/2022 to 30/11/2022 (Three months). | Assistant Engineer |  | ORD/000142/2022-2023 | 790/Kly SD-I | 01/09/2022 | 01/12/2022 | M/S S.K. ENTERPRISE | 0.92 | 0.88 | 95.74 | 0
11 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte.. WEF: 01/06/2022 to 31/08/2022 (Three Months) | Assistant Engineer |  | ORD/000029/2022-2023 | 454/Kly SD-I | 30/05/2022 | 30/08/2022 | SUCHITRA GHOSH | 0.23 | 0.08 | 33.33 | 0
12 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of Ad-hoc Bonus to 06 Nos Laboratory Personnel under Nadia Division PHE dte. for the accounting year 2021-2022. | Assistant Engineer |  | ORD/000163/2022-2023 | 882/Kly SD-I | 21/09/2022 | 28/09/2022 | M/S DIPAK ENTERPRISE | 0.39 | 0.39 | 100 | 0
13 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one no of Lab attendant and one no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. WEF 01/06/2022 to 31/08/2022 (Three months) | Assistant Engineer |  | ORD/000031/2022-2023 | 456/Kly SD-I | 30/05/2022 | 30/08/2022 | M/S S.K. ENTERPRISE | 0.56 | 0.53 | 93.1 | 0
14 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of Maintenance of Nadia District Water Testing Laboratory under Kalyani Sub Division-I under Nadia Division, PHE Dte. W.E.F- 01/09/2022 to 28/02/2023 | Assistant Engineer |  | ORD/000146/2022-2023 | 765/Kly SD-I | 29/08/2022 | 26/02/2023 | MANISHIKA CONSTRUCTION | 0.79 | 0.65 | 83.35 | 0
15 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Engagement of 01 no of lab assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata under Kalyani Sub-Division-1 PHEngineering Dte in the district of Nadia. WEF: 01/02/2022 to 31/05/2022 (Four Months) | Assistant Engineer |  | ORD/000652/2021-2022 | 66/KlySD-I | 25/01/2022 | 25/05/2022 | M/S S.K. ENTERPRISE | 0.4 | 0.4 | 100 | 0
16 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/12/2022 to 28/02/2023 (Three months). | Assistant Engineer |  | ORD/000249/2022-2023 | 1077/Kly SD-1 | 30/11/2022 | 30/03/2023 | M/S S.K. ENTERPRISE | 0.92 | 0.88 | 95.74 | 0
17 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Binoy Badal Dinesh Club for the Month of June'2022 |  |  | VCH/000509/2022-2023 | 95/PFMS | 03/08/2022 | 03/08/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
18 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Bara Andulia Mahila Samity NGO Managed Laboratory for the Month of August'2022. |  |  | VCH/000719/2022-2023 | 269/PFMS | 20/10/2022 | 20/10/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
19 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO Managed Laboratory for the Month of August'2022. |  |  | VCH/000718/2022-2023 | 268/PFMS | 20/10/2022 | 20/10/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
20 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Bara Andulia Mohila Samity for the Month of June'2022 |  |  | VCH/000507/2022-2023 | 93/PFMS | 03/08/2022 | 03/08/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
21 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED WBCADC RANAGHAT-II PROJECT NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. |  |  | VCH/000855/2022-2023 |  | 18/10/2022 | 18/10/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
22 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022. |  |  | VCH/000900/2022-2023 |  | 10/11/2022 | 10/11/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
23 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for WBCADC Ranaghat-II Project NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. |  |  | BILL/00154/2022-2023 | 329/PFMS | 23/12/2022 | 23/12/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
24 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  |  | VCH/001018/2022-2023 | 295/PFMS | 17/11/2022 | 17/11/2022 | BARA ANDULIA MAHILA SAMITY | 0.4 | 0 | 0 | 0
25 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF WBCADC RANAGHAT-II PROJECT. |  |  | VCH/000577/2022-2023 | 168/PFMS | 22/09/2022 | 22/09/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
26 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for WBCADC Ranaghat-II Project for the Month of May'2022. |  |  | VCH/000515/2022-2023 | 101/PFMS | 03/08/2022 | 03/08/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
27 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF WBCADC RANAGHAT-II PROJECT. |  |  | VCH/000789/2022-2023 | 290/PFMS | 17/11/2022 | 17/11/2022 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
28 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. |  |  | VCH/000828/2022-2023 | 240/PFMS | 18/10/2022 | 18/10/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.14 | 0 | 0 | 0
29 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. |  |  | VCH/000829/2022-2023 | 241/PFMS | 18/10/2022 | 18/10/2022 | BARA ANDULIA MAHILA SAMITY | 0.14 | 0 | 0 | 0
30 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Binoy Badal Dinesh Club for the Month of June'2022 |  |  | VCH/000510/2022-2023 | 96/PFMS | 03/08/2022 | 03/08/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
31 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED for the Month of May'2022 |  |  | VCH/000513/2022-2023 | 99/PFMS | 03/08/2022 | 03/08/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
32 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for BINAY BADAL DINESH CLUB for the Month of May'2022 |  |  | VCH/000514/2022-2023 | 100/PFMS | 03/08/2022 | 03/08/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
33 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED HARANAGAR SKUS NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. |  |  | VCH/000856/2022-2023 | 291/PFMS | 17/11/2022 | 17/11/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
34 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED BINOY BADAL DINESH CLUB NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. |  |  | VCH/000859/2022-2023 | 294/PFMS | 17/11/2022 | 17/11/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
35 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Haranagar Samabay Krishi Unnayan Samity Ltd NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. |  |  | BILL/00152/2022-2023 | 330/PFMS | 23/12/2022 | 23/12/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
36 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Haranagar SKUS LTD for the Month of May'2022. |  |  | VCH/000512/2022-2023 | 98/PFMS | 03/08/2022 | 03/08/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
37 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Operation & Mtc fo NGO Managed Lab for Haranagar SKUS Ltd. (1st Installment). |  |  | VCH/000517/2022-2023 | 103/PFMS | 03/08/2022 | 03/08/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.4 | 0 | 0 | 0
38 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR BINOY BADAL DINESH CLUB. |  |  | VCH/000793/2022-2023 | 139/PFMS | 05/09/2022 | 05/09/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
39 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF WBCADC RANAGHAT-II PROJECT. |  |  | VCH/000802/2022-2023 | 135/PFMS | 05/09/2022 | 05/09/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
40 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR BINOY BADAL DINESH CLUB. |  |  | VCH/000581/2022-2023 | 172/PFMS | 22/09/2022 | 22/09/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
41 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  |  | VCH/000901/2022-2023 |  | 10/11/2022 | 10/11/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
42 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Operation & Mtc of NGO Managed Water Testing Lab (Binay Badal Club 2nd Installment). |  |  | VCH/000516/2022-2023 | 102/PFMS | 03/08/2022 | 03/08/2022 | BINAY BADAL DINESH CLUB | 0.35 | 0 | 0 | 0
43 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF HARANAGRA SKUS LTD. |  |  | VCH/000790/2022-2023 | 136/PFMS | 05/09/2022 | 05/09/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
44 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. |  |  | VCH/000857/2022-2023 | 292/PFMS | 17/11/2022 | 17/11/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
45 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  |  | VCH/000903/2022-2023 |  | 10/11/2022 | 10/11/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
46 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of WBCADC Ranaghat -II Project NGO Managed Laboratory for the Month of August'2022. |  |  | VCH/000716/2022-2023 | 266/PFMS | 20/10/2022 | 20/10/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
47 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Haranagar Samabay Krishi Unnayan Samity LTD NGO Managed Laboratory for the Month of August'2022. |  |  | VCH/000717/2022-2023 | 267/PFMS | 20/10/2022 | 20/10/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
48 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly Remuneration of 01 No. Chemist, 01 No. Bacteriologist and 01 No. Lab Assistant of Binoy Badal Dinesh Club NGO Managed Laboratory for the Month of August'2022. |  |  | VCH/000720/2022-2023 | 270/PFMS | 20/10/2022 | 20/10/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
49 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY. |  |  | VCH/000579/2022-2023 | 170/PFMS | 22/09/2022 | 22/09/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
50 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Haranagar SKUS Ltd Project for the Month of June'2022 |  |  | VCH/000508/2022-2023 | 94/PFMS | 03/08/2022 | 03/08/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
51 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB BARA ANDULIA MAHILA SAMITY. |  |  | VCH/000792/2022-2023 | 138/PFMS | 05/09/2022 | 05/09/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
52 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. |  |  | VCH/000830/2022-2023 | 242/PFMS | 18/10/2022 | 18/10/2022 | BINAY BADAL DINESH CLUB | 0.14 | 0 | 0 | 0
53 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE OF NGO MANAGED WATER TESTING LABORATORIES [HARANAGAR SKUS LTD] AT NADIA DISTRICT. |  |  | VCH/000912/2022-2023 | 302/PFMS | 17/11/2022 | 17/11/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.35 | 0 | 0 | 0
54 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF HARANAGRA SKUS LTD. |  |  | VCH/000578/2022-2023 | 169/PFMS | 22/09/2022 | 22/09/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
55 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE OF NGO MANAGED WATER TESTING LABORATORIES [ BARA ANDULIA MAHILA SAMITY] AT NADIA DISTRICT. |  |  | VCH/000905/2022-2023 |  | 10/11/2022 | 10/11/2022 | BARA ANDULIA MAHILA SAMITY | 0.4 | 0 | 0 | 0
56 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for WBCADC Ranaghat-II Project for the Month of June'2022 |  |  | VCH/000506/2022-2023 | 92/PFMS | 03/08/2022 | 03/08/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
57 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL OF NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY. |  |  | VCH/000791/2022-2023 | 137/PFMS | 05/09/2022 | 05/09/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
58 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. |  |  | VCH/000826/2022-2023 | 238/PFMS | 18/10/2022 | 18/10/2022 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.14 | 0 | 0 | 0
59 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Nadia Zill M0hila Samabay Rindan Samity Limited NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. |  |  | BILL/00153/2022-2023 | 331/PFMS | 23/12/2022 | 23/12/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
60 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB BARA ANDULIA MAHILA SAMITY. |  |  | VCH/000580/2022-2023 | 171/PFMS | 22/09/2022 | 22/09/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
61 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  |  | VCH/000904/2022-2023 |  | 10/11/2022 | 10/11/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
62 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF NGO LAB PERSONNEL FOR 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR THE MONTH OF OCTOBER'2022 |  |  | VCH/000902/2022-2023 |  | 10/11/2022 | 10/11/2022 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
63 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | AD-HOC BONUS BILL FOR NGO LAB PERSONNEL (01 NO. CHEMIST, 01 NO. BACTERIOLOGIST AND 01 NOS LAB ATTENDANT) FOR THE YEAR 2021-2022. |  |  | VCH/000827/2022-2023 | 239/PFMS | 18/10/2022 | 18/10/2022 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.14 | 0 | 0 | 0
64 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Bara Andulia Mahila Samity, NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. |  |  | BILL/00150/2022-2023 | 332/PFMS | 23/12/2022 | 23/12/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
65 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Binoy Badal Dinesh Club NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. |  |  | BILL/00151/2022-2023 | 333/PFMS | 23/12/2022 | 23/12/2022 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
66 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Honorarium for Lab Personnel for Bara Andulia Mohila Samity for the Month of May'2022. |  |  | VCH/000511/2022-2023 | 97/PFMS | 03/08/2022 | 03/08/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
67 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ATTENDED BARA ANDULIA MAHILA SAMITY NGO MANAGED LABORATORY FOR THE MONTH OF SEPTEMBER-2022. |  |  | VCH/000858/2022-2023 | 293/PFMS | 17/11/2022 | 17/11/2022 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
68 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/03/2023 to 31/05/2023 (Three months) | Assistant Engineer |  | ORD/000433/2022-2023 | 273/Kly SD-I | 28/02/2023 | 31/05/2023 | JOYDEV JANA | 0.5 | 0.5 | 100 | 0
69 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/03/2023 to 31/05/2023 (Three months) | Assistant Engineer |  | ORD/000434/2022-2023 | 274/Kly SD-I | 28/02/2023 | 31/05/2023 | GOUTAM DAM | 0.5 | 0.5 | 100 | 0
70 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/03/2023 to 31/05/2023 (Three months) | Assistant Engineer |  | ORD/000435/2022-2023 | 275/Kly SD-I | 28/02/2023 | 31/05/2023 | SUCHITRA GHOSH | 0.23 | 0.23 | 100 | 0
71 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/03/2023 to 31/05/2023 (Three months) | Assistant Engineer |  | ORD/000436/2022-2023 | 276/ Kly SD-I | 28/02/2023 | 31/05/2023 | M/S S.K. ENTERPRISE | 0.92 | 0.92 | 100 | 0
72 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/04/2023 to 30/06/2023 (Three months). | Assistant Engineer |  | ORD/000543/2022-2023 | 461/ Kly SD-1 | 31/03/2023 | 30/06/2023 | M/S S.K. ENTERPRISE | 0.8 | 0.8 | 100 | 0
73 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Engagement of 01 no of Chemist cum Operator of Atomic Absorption Spectrophotometer (AAS) at Nadia District Water Testing Laboratory under Nadia Division, P.H.E Dte WEF: 01/07/2023 to 30/09/2023 (Three months). | Assistant Engineer |  | ORD/000094/2023-2024 | 734/KLYSD-I | 27/06/2023 | 27/09/2023 | M/S S.K. ENTERPRISE | 0.8 | 0 | 0 | 0
74 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.03.2023 to 30.04.2023 (Two Month). | Assistant Engineer |  | ORD/000510/2022-2023 | 854/ND | 28/02/2023 | 30/04/2023 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 2.68 | 98.29 | 0
75 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation for Payment of remuneration for engagement of 10 nos. personnel (One Chemist / Bacteriologist and one Lab Assistant) at 5 Nos. Sub-District Laboratories under Nadia Division, P.H.E. Dte. on contractual basis w.e.f. 01.05.2023 to 30.06.2023 (Two Month). | Assistant Engineer |  | ORD/000047/2023-2024 | 1939/ND | 28/04/2023 | 28/06/2023 | CLIFFORD FACILITY SERVICES PVT. LTD | 2.73 | 1.36 | 50 | 50
76 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation work order for Engagement of 01 no of Bacteriologist /Analyst for operation and maintenance of Bacteriological testing unit of Nadia Divisional Laboratory Under Kalyani SD-1, P.H.Engineering Dte WEF: 01/06/2023 to 31/08/2023 (Three months) |  | Junior Engineer 2 | ORD/000061/2023-2024 | 657/KlySD-I | 24/05/2023 | 24/08/2023 | GOUTAM DAM | 0.5 | 0.33 | 66.67 | 70
77 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation work order for Engagement of 01 no of Sampling assistant for operation and maintenance of physic-chemical testing unit and bacteriological testing unit of Nadia Water Testing Laboratory under PHE Dte. WEF: 01/06/2023 to 31/08/2023 (Three months) |  | Junior Engineer 2 | ORD/000062/2023-2024 | 658/KLYSD-I | 24/05/2023 | 24/08/2023 | SUCHITRA GHOSH | 0.23 | 0.15 | 66.67 | 70
78 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation work order for Engagement of 01 no of Chemist /Analyst for operation and maintenance of physico-Chemical testing unit of Nadia Divisional Laboratory at W.T.P, Haringhata Under Kalyani SD-1, PHE Dte in the district of Nadia. WEF: 01/06/2023 to 31/08/2023 (Three months) |  | Junior Engineer 2 | ORD/000060/2023-2024 | 656/KLYSD-I | 24/05/2023 | 24/08/2023 | JOYDEV JANA | 0.5 | 0.33 | 66.67 | 70
79 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Continuation of Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/06/2023 to 31/08/2023 (Three months) | Assistant Engineer |  | ORD/000096/2023-2024 | 670/KLYSD-I | 29/05/2023 | 29/08/2023 | M/S S.K. ENTERPRISE | 0.92 | 0.92 | 100 | 100
80 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Secretary Bara Andulia Mahila Samity) under Nadia Divn. PHE Dte. for the month of Jan'2023. |  |  | BILL/00613/2022-2023 | 448/PFMS | 06/03/2023 | 06/03/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
81 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for BARA ANDULIA MAHILA SAMITY. |  |  | BILL/00686/2022-2023 |  | 25/03/2023 | 25/03/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
82 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for BINAY BADAL DINESH CLUB |  |  | BILL/00687/2022-2023 |  | 25/03/2023 | 25/03/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
83 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( BINAY BADAL DINESH CLUB) under Nadia Divn. PHE Dte. for the month of Feb'2023. |  |  | BILL/00727/2022-2023 | 516/PFMS | 28/03/2023 | 28/03/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
84 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for W.B.C.A.D.C. RANAGHAT-II |  |  | BILL/00684/2022-2023 |  | 25/03/2023 | 25/03/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
85 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | BILL FOR LABORATORY ANNUAL MAINTENANCE CHARGE 2ND INSTALLMENT FOR FY 2021-2022 FOR BARA ANDULIA MAHILA SAMITY NGO LAB. |  |  | BILL/00263/2023-2024 | 125/PFMS | 26/06/2023 | 26/06/2023 | BARA ANDULIA MAHILA SAMITY | 0.35 | 0 | 0 | 0
86 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS LTD NGO LAB FOR THE MONTH OF JUNE-23. |  |  | BILL/00407/2023-2024 | 190/PFMS | 20/07/2023 | 20/07/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
87 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for WBCADC Ranaghat-II Project NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December¿ 2022. |  |  | BILL/00272/2022-2023 | 389/PFMS | 30/01/2023 | 30/01/2023 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
88 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Binoy Bdal Dinesh Club NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December¿ 2022. |  |  | BILL/00271/2022-2023 | 393/PFMS | 30/01/2023 | 30/01/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
89 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Officer in charge WBCADC Ranaghat -II project) under Nadia Divn. PHE Dte. for the month of Jan'2023. |  |  | BILL/00612/2022-2023 | 445/PFMS | 06/03/2023 | 06/03/2023 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
90 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF APRIL-23. |  |  | BILL/00106/2023-2024 | 45/PFMS | 02/06/2023 | 02/06/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
91 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( NADIA ZILLA GANATANTRIK) under Nadia Divn. PHE Dte. for the month of Jan'2023. |  |  | BILL/00725/2022-2023 | 514/PFMS | 28/03/2023 | 28/03/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
92 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF MAY-23. |  |  | BILL/00229/2023-2024 | 101/PFMS | 13/06/2023 | 13/06/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
93 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAR RINDAN SAMITY LIMITED NGO LAB FOR THE MONTH OF JULY-23. |  |  | BILL/00491/2023-2024 | 224/PFMS | 11/08/2023 | 11/08/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
94 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE OF NGO MANAGED WATER TESTING LABORATORY AT NADIA DISTRICT. |  |  | BILL/00511/2023-2024 |  | 18/08/2023 | 18/08/2023 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0 | 0
95 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Haranagar S.K.U.S LTD) under Nadia Divn. PHE Dte. for the month of Jan'2023. |  |  | BILL/00610/2022-2023 | 446/PFMS | 06/03/2023 | 06/03/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
96 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD NGO LABORATORY FOR THE MONTH OF MARCH'2023. |  |  | BILL/00024/2023-2024 | 27/PFMS | 12/05/2023 | 12/05/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
97 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR BARA ANDULIA MAHILA SAMITY NGO LABORATORY FOR THE MONTH OF MARCH'2023. |  |  | BILL/00025/2023-2024 | 29/PFMS | 12/05/2023 | 12/05/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
98 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADA DINESH CLUB NGO LAB FOR THE MONTH OF MAY-23. |  |  | BILL/00230/2023-2024 | 102/PFMS | 13/06/2023 | 13/06/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
99 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMITY NGO LAB FOR THE MONTH OF JUNE-23. |  |  | BILL/00408/2023-2024 | 191/PFMS | 20/07/2023 | 20/07/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
100 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II PROJECT NGO LAB FOR THE MONTH OF JUNE-23. |  |  | BILL/00406/2023-2024 | 189/PFMS | 20/07/2023 | 20/07/2023 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
101 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December¿ 2022. |  |  | BILL/00274/2022-2023 | 391/PFMS | 30/01/2023 | 30/01/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
102 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for Haranagar SKUS. |  |  | BILL/00683/2022-2023 |  | 25/03/2023 | 25/03/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
103 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( B.B.D CLUB) under Nadia Divn. PHE Dte. for the month of Feb'23. |  |  | BILL/00723/2022-2023 | 512/PFMS | 28/03/2023 | 28/03/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
104 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR W.B.C.A.D.C. RANAGHAT-II PROJECT NGO LABORATORY FOR THE MONTH OF MARCH'2023. |  |  | BILL/00027/2023-2024 | 26/PFMS | 12/05/2023 | 12/05/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
105 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF APRIL-23. |  |  | BILL/00107/2023-2024 | 46/PFMS | 02/06/2023 | 02/06/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
106 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | OPERATION AND MAINTENANCE CHARGE OF HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD NGO LABORATORY ( FIRST INSTALLMENT FOR THE YEAR 2022-2023). |  |  | BILL/00037/2023-2024 | 25/PFMS | 12/05/2023 | 12/05/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.4 | 0 | 0 | 0
107 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II NGO LAB FORTHE MONTH OF MAY-23. |  |  | BILL/00226/2023-2024 | 98/PFMS | 13/06/2023 | 13/06/2023 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
108 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF JUNE-23. |  |  | BILL/00410/2023-2024 | 193/PFMS | 20/07/2023 | 20/07/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
109 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF JULY-23. |  |  | BILL/00492/2023-2024 | 226/PFMS | 11/08/2023 | 11/08/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
110 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( B.B.D CLUB) under Nadia Divn. PHE Dte. for the month of Jan'23. |  |  | BILL/00611/2022-2023 | 449/PFMS | 06/03/2023 | 06/03/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
111 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS NGO LAB FOR THE MONTH OF MAY-23. |  |  | BILL/00227/2023-2024 | 99/PFMS | 13/06/2023 | 13/06/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
112 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL CLUB NGO LAB FOR THE MONTH OF AUGUST-23. |  |  | BILL/00584/2023-2024 | 264/PFMS | 13/09/2023 | 13/09/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
113 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Haranagar Samabay Krishi Unnayan Samity Ltd NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of December- 2022. |  |  | BILL/00270/2022-2023 | 390/PFMS | 30/01/2023 | 30/01/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
114 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment of honorarium for Bara Andulia Mahila Samity NGO Laboratory Personnel (01 No. Chemist, 01 No. Bacteriologist and 01 No. Laboratory Assistant) for the month of November¿ 2022. |  |  | BILL/00273/2022-2023 | 392/PFMS | 30/01/2023 | 30/01/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
115 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( BARA ANDULIA MAHILA SAMITY) under Nadia Divn. PHE Dte. for the month of Jan'2023. |  |  | BILL/00726/2022-2023 | 515/PFMS | 28/03/2023 | 28/03/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
116 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF JULY-23. |  |  | BILL/00494/2023-2024 | 226/PFMS | 11/08/2023 | 11/08/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
117 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR NGO LAB FOR THE MONTH OF AUGUST-23. |  |  | BILL/00581/2023-2024 | 262/PFMS | 13/09/2023 | 13/09/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
118 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II PROJECT NGO LAB FOR THE MONTH OF AUGUST-23. |  |  | BILL/00580/2023-2024 | 261/PFMS | 13/09/2023 | 13/09/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
119 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MAHILA SAMITY NGO LAB FOR THE MONTH OF AUGUST-23. |  |  | BILL/00583/2023-2024 | 264/PFMS | 13/09/2023 | 13/09/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
120 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LABORATORY FOR THE MONTH OF MARCH'2023. |  |  | BILL/00028/2023-2024 | 30/PFMS | 12/05/2023 | 12/05/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
121 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF 01 NO. CHEMIST, 01 NO. BACTERIOLOGIST, 01 NO. LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LABORATORY FOR THE MONTH OF MARCH'2023. |  |  | BILL/00029/2023-2024 | 28/PFMS | 12/05/2023 | 12/05/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
122 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Monthly remuneration of NGO Lab personnel for the Month of Feb'2023 for NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED |  |  | BILL/00685/2022-2023 |  | 25/03/2023 | 25/03/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
123 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRICT MOHILA SAMITY NGO LAB FOR THE MONTH OF MAY-23. |  |  | BILL/00228/2023-2024 | 100/PFMS | 13/06/2023 | 13/06/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
124 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMITY NGO LAB FOR THE MONTH OF APRIL-23. |  |  | BILL/00104/2023-2024 | 44/PFMS | 02/06/2023 | 02/06/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
125 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF JUNE-23. |  |  | BILL/00409/2023-2024 | 192/PFMS | 20/07/2023 | 20/07/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
126 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED) under Nadia Divn. PHE Dte. for the month of Jan'2023. |  |  | BILL/00614/2022-2023 | 447/PFMS | 06/03/2023 | 06/03/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
127 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | Payment for monthly remuneration for laboratory personnel of NGO managed laboratories( Haranagar S.K.U.S LTD) under Nadia Divn. PHE Dte. for the month of Feb'2023. |  |  | BILL/00724/2022-2023 | 513/PFMS | 28/03/2023 | 28/03/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
128 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS NGO LAB FOR THE MONTH OF JULY-23. |  |  | BILL/00490/2023-2024 | 223/PFMS | 11/08/2023 | 11/08/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
129 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SKUS NGO LAB FORTHE MONTH OF APRIL-23. |  |  | BILL/00103/2023-2024 | 43/PFMS | 02/06/2023 | 02/06/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
130 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II PROJECT NGO LAB FOR THE MONTH OF APRIL-23. |  |  | BILL/00105/2023-2024 | 42/PFMS | 02/06/2023 | 02/06/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
131 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA WBCADC RANAGHAT-II NGO LAB FOR THE MONTH OF JULY-23. |  |  | BILL/00493/2023-2024 | 222/PFMS | 11/08/2023 | 11/08/2023 | OFFICER IN-CHARGE, W.B.C.A.D.C RANAGHAT -II PROJECT | 0.33 | 0 | 0 | 0
132 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Water Testing Laboratories under Nadia Division, PHE Dte related to Water Quality Monitoring & Survillance under Jal Jeevan Mission. | SM/11522 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LAB FOR THE MONTH OF AUGUST-23. |  |  | BILL/00582/2023-2024 | 263/PFMS | 13/09/2023 | 13/09/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
Total | [13 empty] | 74.93 | 37.11 | 49.53