## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Magurkhali W/S Scheme in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000443/2021-2022 | 1063/RSD | 02/12/2021 | 01/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.76 | 4.76 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Magurkhali to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000299/2022-2023 | 5355/ND | 22/12/2022 | 25/02/2026 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 586.94 | 480.1 | 81.8 | 90
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 1of Magurkhali W/S scheme of Ranaghat-II block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000233/2022-2023 | 560/RSD | 31/08/2022 | 30/09/2022 | M/S ARNAB CONSTRUCTION | 4.68 | 3.52 | 75.17 | 100
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Special repair & renovation of boundary wall & allied works in the premises at pump house no 3 of Magurkhali W/S scheme of Ranaghat-II block under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000234/2022-2023 | 560/A/RSD | 31/08/2022 | 30/09/2022 | ASOKE KUMAR DUTTA | 4.49 | 2.17 | 48.32 | 100
5 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Magurkhali W/S Scheme (T/W-I), Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000099/2023-2024 | 901/CDD | 18/07/2023 | 17/08/2023 | UTTAM KUMAR CHATTERJEE | 18.6 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MAGURKHALI W/S Scheme, Block- RANAGHAT II , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 1580/EMD | 24/04/2023 | 16/05/2025 | ESENCE ENGINEERING CONCERN | 21.64 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 24/ND | 03/01/2023 | 03/01/2023 | Resource Division | 24.14 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 2311/ND | 29/05/2023 | 29/05/2023 | Resource Division | 44.59 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Additional work of Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Magurkhali to accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000111/2024-2025 | 4344/ND | 07/08/2024 | 28/05/2026 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 78.93 | 0 | 0 | 60
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-2 site at Magurkhali Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000304/2024-2025 | 1280/RSD | 04/10/2024 | 18/12/2024 | R.R.ENTERPRISE | 4.45 | 1.16 | 26.05 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Magurkhali piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000179/2024-2025 | 1147/RSD | 11/09/2024 | 26/10/2024 | M/S RANA ENTERPRISE | 1.9 | 0 | 0 | 100
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 7560/ND | 27/12/2024 | 27/12/2024 | Resource Division | 8.2 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Magurkhali under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000889/2024-2025 | 201/RSD | 06/02/2025 | 23/03/2025 | SAYANTAN PANDEY | 2.15 | 0 | 0 | 100
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAGURKHALI to Accommodate FHTC in Ranaghat-II block of Nadia District under Nadia Division PHE Dte. | SM/11546 | Augmentation | New Service connection charges for MAGURKHALI W/S SCHEME Pump House No- IV |  |  | BILL/00817/2024-2025 | 137/JJM QTN | 22/08/2025 | 22/08/2025 | WBSEDCL RANAGHAT (EAST) CCC | 3.56 | 0 | 0 | 0
Total | [13 empty] | 906 | 491.7 | 54.27