## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 4932/ND | 25/11/2022 | 25/11/2022 | Resource Division | 38.64 | 0 | 0 | 0
2 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Naserkhuli W/S Scheme (Z- II, T/W-II),Ranaghat-II Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000067/2023-2024 | 511/CDD | 01/06/2023 | 01/07/2023 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 4326/ND | 29/09/2022 | 29/09/2022 | Resource Division | 18.4 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 2284/ND | 29/05/2023 | 29/05/2023 | Resource Division | 18.4 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | SHIFTING OF LT OH POLE AT NASERKHULI Z-II HEAD WORK SITE PWSS |  |  | BILL/00337/2024-2025 | 242/PFMS | 13/09/2024 | 13/09/2024 | WBSEDCL RANAGHAT (EAST) CCC | 0.53 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | Laying of distribution system including specials, valves & pipe supporting structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-II to accommodate FHTC within Ranaghat-II Dev. Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. (sm/11547) | Assistant Engineer | Junior Engineer 4 | ORD/000177/2022-2023 | 4382/ND | 13/10/2022 | 11/03/2025 | M/S GHOSH CONSTRUCTION | 332.64 | 0 | 0 | 96
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-II to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11547 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 524.45 | 0 | 0