## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 3/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-III in Krishnanagar II Block under Krishnanagar Sub Division, PHE Dte. ( Sl.No .05 ) | Assistant Engineer |  | ORD/000714/2021-2022 | 207/KSD | 04/03/2022 | 19/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.42 | 4.37 | 99.01 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000161/2022-2023 | 86/ND | 05/01/2023 | 05/01/2023 | Resource Division | 222.47 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 366 days w.e.f. 01/01/2024 to 31/12/2024 | Assistant Engineer | Junior Engineer 3 | ORD/000758/2023-2024 | 1838/KSD | 28/12/2023 | 28/12/2024 | TARUN KUMAR BHATTACHARYA | 4.8 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | RESTORATION OF ROAD FROM SALIGRAM POST OFFICE - CHUPIPOTA VILLAGE under Package No. WB/14/135 |  |  | BILL/00504/2024-2025 | 300/PFMS | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 10.95 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3,Junior Engineer 4,Junior Engineer 5 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 01/10/2026 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 452.19 | 4.77 | 20
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 16/03/2025 | BIBHAS PAL | 96.01 | 0 | 0 | 30
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 3 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 31/12/2025 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11609 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 11/12/2025 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
Total | [13 empty] | 10550.39 | 456.57 | 4.33