## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 5A of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000774/2021-2022 | 124/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.88 | 4.88 | 100 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000120/2022-2023 | 74/ND | 05/01/2023 | 05/01/2023 | Resource Division | 66.06 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-IB to Zone-IVB) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000339/2023-2024 | 985/KLYSD-I | 11/09/2023 | 10/12/2023 | TECHVISION | 4.85 | 4.85 | 100 | 100
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Health Check up of existing Over Head Reservoir(OHR) based on inspection and Non-destructive Test (NDT) at Northern Sector Part-I (Zone-5A) PWSS at Kaligunj Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000103/2024-2025 | 4279/ND | 05/08/2024 | 20/08/2024 | JADAVPUR UNIVERSITY | 3.48 | 3.48 | 100 | 100
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 01/04/2026 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 739.79 | 4.5 | 47
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Making 6(six) nos barbed wire fencing with concrete pillars at Different Zonal Sites of Surface Water Based Water Supply Scheme Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000012/2025-2026 | 1776/ND | 21/04/2025 | 20/06/2025 | TARUN KUMAR BHATTACHARYA | 27.41 | 13.71 | 50 | 100
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/A (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11649 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 10/04/2026 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
Total | [13 empty] | 17287 | 766.71 | 4.44