## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 9/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000807/2021-2022 | 157/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.66 | 4.63 | 99.24 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 700 cum. for Providing FHTC (Functional Household Tap Connection) for Zone IX/A Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000258/2023-2024 | 4007/ND | 07/09/2023 | 06/11/2023 | CHANDAN ROY | 27.44 | 9.67 | 35.22 | 30
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 21/09/2026 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 300.51 | 13.04 | 19
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2026 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 248/ND | 11/01/2024 | 11/01/2024 | Resource Division | 7.22 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11652 | Augmentation | Restoration of Bholadanga welcome gate to Bangoria over Bridge via NH 34 |  |  | BILL/00511/2024-2025 | 302/PFMS | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 20.27 | 0 | 0 | 0
Total | [13 empty] | 3968.22 | 316.2 | 7.97