## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 1049/RSD | 02/12/2021 | 01/01/2022 | HORIZEN | 3.01 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1864/ND | 26/04/2023 | 26/04/2023 | Resource Division | 58.87 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bagula Zone-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000107/2024-2025 | 4341/ND | 07/08/2024 | 03/02/2025 | AMIT KUMAR BOSE | 181.56 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 255/ND | 11/01/2024 | 11/01/2024 | Resource Division | 10.78 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 7563/ND | 27/12/2024 | 27/12/2024 | Resource Division | 31.61 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of 55.0 m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 2nd Tube Well site. | Assistant Engineer | Junior Engineer 3 | ORD/000794/2024-2025 | 84/RSD | 14/01/2025 | 30/03/2025 | B P ENTERPRISE | 4.87 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of 111.60 m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 1st Tube Well site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000751/2024-2025 | 459/ND | 29/01/2025 | 29/04/2025 | BUDDHADEV MONDAL | 9.5 | 0 | 0 | 0
Total | [13 empty] | 397.18 | 0 | 0