## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000429/2021-2022 | 1049/RSD | 02/12/2021 | 01/01/2022 | HORIZEN | 3.01 | 2.59 | 85.85 | 100
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Bagula Zone-I to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000148/2023-2024 | 3215/ND | 26/07/2023 | 26/07/2026 | BANERJEE CONSTRUCTION, RAJA RAM MOHAN PALLY,BARASAT, KOLKATA-700124 | 222.67 | 0 | 0 | 65
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1864/ND | 26/04/2023 | 26/04/2023 | Resource Division | 58.87 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Bagula Zone-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000107/2024-2025 | 4341/ND | 07/08/2024 | 02/08/2025 | AMIT KUMAR BOSE | 181.56 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Bagula Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000377/2024-2025 | 1412/RSD | 19/11/2024 | 03/01/2025 | S.M.ENTERPRISE | 2.15 | 0 | 0 | 95
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Bagula Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000207/2024-2025 | 1144/RSD | 11/09/2024 | 26/10/2024 | ANNESHA CONSTRUCTION | 1.89 | 1.73 | 91.17 | 100
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2023-2024 | 255/ND | 11/01/2024 | 11/01/2024 | Resource Division | 10.78 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 7563/ND | 27/12/2024 | 27/12/2024 | Resource Division | 31.61 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of 55.0 m Boundary Wall (2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 2nd Tube Well site. | Assistant Engineer | Junior Engineer 3 | ORD/000794/2024-2025 | 84/RSD | 14/01/2025 | 27/08/2025 | B P ENTERPRISE | 4.87 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of 111.60 m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Bagula Zone-I PWSS 1st Tube Well site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000751/2024-2025 | 459/ND | 29/01/2025 | 26/10/2025 | BUDDHADEV MONDAL | 9.5 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of Jhama Bats Road at Bagula Zone -I water supply scheme under Ranaghat Sub Division under Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000806/2024-2025 | 203/RSD | 06/02/2025 | 08/03/2025 | APURBA MANDAL | 6.91 | 0 | 0 | 100
13 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA | SM/11740 | Augmentation | Construction of Pile foundation, Pile Cap, Padestal, Tie Beam for Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir for BAGULA ZONE-I Piped Water Supply scheme under Nadia Division P.H.E. Dte. in the District of Nadia | Assistant Engineer | Junior Engineer 3 | ORD/000038/2025-2026 | 2175/ND | 07/05/2025 | 05/08/2025 | BANERJEE CONSTRUCTION | 50.8 | 0 | 0 | 100
Total | [13 empty] | 681.61 | 7.11 | 1.04