## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000446/2021-2022 | 1066/RSD | 02/12/2021 | 01/01/2022 | HORIZEN | 3.01 | 2.91 | 96.54 | 100
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Bagula Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer 3 | ORD/000398/2023-2024 | 5188/ND | 22/11/2023 | 20/02/2024 | M/S S.K. ENTERPRISE | 6.88 | 0 | 0 | 0
3 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bagula (Z-II) PWSS W/S Scheme (TW-I) ,Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000141/2023-2024 | 1661/CDD | 17/10/2023 | 16/11/2023 | RAJ & ENTERPRISE | 18.71 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1865/ND | 26/04/2023 | 26/04/2023 | Resource Division | 12.06 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
6 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-II under Bagula Zone-II ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2024-2025 | 1305/EMD | 09/05/2024 | 31/07/2025 | ANUPAMA ENGINEERING WORKS | 9.26 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 256/ND | 11/01/2024 | 11/01/2024 | Resource Division | 25.16 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 7558/ND | 27/12/2024 | 27/12/2024 | Resource Division | 3.66 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Construction of 120.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Bagula Zone-II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000078/2024-2025 | 4124/ND | 29/07/2024 | 19/07/2026 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 296.58 | 0 | 0 | 70
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Bagula Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000378/2024-2025 | 1413/RSD | 19/11/2024 | 03/01/2025 | J & T ENTERPRISE | 2.15 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Bagula Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000204/2024-2025 | 1140/RSD | 11/09/2024 | 26/10/2024 | MUKHERJEE CONSTRUCTION | 1.9 | 0.37 | 19.7 | 90
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Surging of 05(Five) nos. big dia tube well at Bagula Zone-II (Tubewell No- 1 & 2), Nutangram (Tubewell No-I), Hudachapra (Tubewell No-2) & Fatepur (Tubewell No-1) water supply schemes under Ranaghat Sub-Division under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000138/2024-2025 | 876/RSD | 20/08/2024 | 20/09/2024 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.84 | 0 | 0 | 100
13 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, construction of 550 cum capacity 20 mtr. Staging height RCC over head reservoir (including pile foundation), pipe connection and cost of pipes, specials and soil investigation for construction of one no. 550 cum OHR of staging height 20 mtr. for augmentation of Ground Water Based Water Supply Scheme for BAGULA Zone-II to accommodate FHTC in Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000205/2023-2024 | 3540/ND | 11/08/2023 | 11/08/2025 | AMAL DUTTA ROY | 565.73 | 92.68 | 16.38 | 70
Total | [13 empty] | 1044.91 | 98.76 | 9.45