## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Bagula Zone-II W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000446/2021-2022 | 1066/RSD | 02/12/2021 | 01/01/2022 | HORIZEN | 3.01 | 2.91 | 96.54 | 100
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Bagula Zone-II Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer 3 | ORD/000398/2023-2024 | 5188/ND | 22/11/2023 | 20/02/2024 | M/S S.K. ENTERPRISE | 6.88 | 0 | 0 | 0
3 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Bagula (Z-II) PWSS W/S Scheme (TW-I) ,Hanskhali Block under Nadia District, Central Drilling Division, P.H.E. Dte. |  |  | ORD/000141/2023-2024 | 1661/CDD | 17/10/2023 | 16/11/2023 | RAJ & ENTERPRISE | 18.71 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1865/ND | 26/04/2023 | 26/04/2023 | Resource Division | 12.06 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
6 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-II under Bagula Zone-II ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2024-2025 | 1305/EMD | 09/05/2024 | 31/07/2025 | ANUPAMA ENGINEERING WORKS | 9.26 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000138/2023-2024 | 256/ND | 11/01/2024 | 11/01/2024 | Resource Division | 25.16 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 7558/ND | 27/12/2024 | 27/12/2024 | Resource Division | 3.66 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Construction of 120.00 Cum/Hr capacity Arsenic-cum-Iron Removal plant at Bagula Zone-II Water Supply Scheme under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000078/2024-2025 | 4124/ND | 29/07/2024 | 19/07/2026 | ODISSI INNOVATIONS ENGINEERS PRIVATE LIMITED | 296.58 | 0 | 0 | 70
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Bagula Zone-II under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000378/2024-2025 | 1413/RSD | 19/11/2024 | 03/01/2025 | J & T ENTERPRISE | 2.15 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Bagula Zone-II piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000204/2024-2025 | 1140/RSD | 11/09/2024 | 26/10/2024 | MUKHERJEE CONSTRUCTION | 1.9 | 0.37 | 19.7 | 90
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-II BLOCK: HANSKHALI DISTRICT: NADIA | SM/11741 | Augmentation | Surging of 05(Five) nos. big dia tube well at Bagula Zone-II (Tubewell No- 1 & 2), Nutangram (Tubewell No-I), Hudachapra (Tubewell No-2) & Fatepur (Tubewell No-1) water supply schemes under Ranaghat Sub-Division under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000138/2024-2025 | 876/RSD | 20/08/2024 | 20/09/2024 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.84 | 0 | 0 | 100
Total | [13 empty] | 479.18 | 6.08 | 1.27