## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 2/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000787/2021-2022 | 137/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.29 | 3.78 | 88.16 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 93/ND | 05/01/2023 | 05/01/2023 | Resource Division | 102.91 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 700 cum. For Surface Water Based Piped Water Supply Scheme for Zone II/A (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.¿ | Assistant Engineer | Junior Engineer 3 | ORD/000262/2023-2024 | 3999/ND | 07/09/2023 | 06/11/2023 | S.B.CONSTRUCTION | 27.73 | 27.66 | 99.73 | 50
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 228/ND | 11/01/2024 | 11/01/2024 | Resource Division | 10.18 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Additional work for Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes etc. all complete for Zone- II/A (Northern Sector Part-II) under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000864/2024-2025 | 1473/ND | 25/03/2025 | 24/05/2025 | ONKAR ENTERPRISE | 72.83 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000310/2023-2024 | 4280/ND | 21/09/2023 | 10/12/2025 | ONKAR ENTERPRISE | 284.27 | 85.42 | 30.05 | 4
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11808 | Augmentation | Restoration of road under Augmentation of Surface Water Based PWSS at Northern Sector Part II (Zone II/A) at Nakashipara block under Debagram Sub Division PHE DTE. | Assistant Engineer | Junior Engineer 1 | ORD/000688/2024-2025 | 1063/DSD | 30/12/2024 | 14/01/2025 | S.M.ENTERPRISE | 4.85 | 4.8 | 99 | 100
Total | [13 empty] | 604.02 | 124.46 | 20.6