## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 3/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000790/2021-2022 | 140/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.91 | 3.87 | 98.9 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 125/ND | 05/01/2023 | 05/01/2023 | Resource Division | 73.72 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Reconstruction of Top Dome and other related work for 455 cum RCC elevated reservoir of Surface Water Based Water Supply Scheme for Zone-III /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000188/2024-2025 | 6096/ND | 19/09/2024 | 18/12/2024 | M/S SANJAY ADHIKARI | 9.82 | 9.75 | 99.34 | 5
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 230/ND | 11/01/2024 | 11/01/2024 | Resource Division | 10.27 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Restoration work of damaged road flank of Dharmadha - Muragacha Road due to laying pipe line under ''NJJM'' Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Dharmada - Muragacha Road from 0.80 kmp to 1.50 kmp (one side) & from 1.50 kmp to 3.70 kmp (both side) of Krishnagar Highway Sub-Division-I under Nadia Highway Division-I in the district of Nadia during the year 2024-2025. |  |  | BILL/00250/2024-2025 |  | 26/07/2024 | 26/07/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 14.83 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Restoration work of damaged road flank of Dharmadha - Muragacha Road due to laying pipe line under ''NJJM'' Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Dharmada - Muragacha Road from 0.80 kmp to 1.50 kmp (one side) & from 1.50 kmp to 3.70 kmp (both side) of Krishnagar Highway Sub-Division-I under Nadia Highway Division-I in the district of Nadia during the year 2024-2025. |  |  | BILL/00344/2024-2025 | 149/PFMS | 06/08/2024 | 06/08/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 7.41 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 25/03/2026 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 288.84 | 12.53 | 19
9 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2026 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
10 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Reconstruction of Staff room, Chlorination room, Godown, Boundary wall, Service road and etc. of Surface Water Based Water Supply Scheme for Zone-III /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000189/2024-2025 | 6097/ND | 19/09/2024 | 14/09/2025 | M/S SANJAY ADHIKARI | 55.82 | 6.94 | 12.43 | 5
11 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 08/10/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
12 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 455 cum. of Surface Water Based Piped Water Supply Scheme for Zone- III/ A (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer 3 | ORD/000264/2023-2024 | 4000/ND | 07/09/2023 | 01/12/2024 | M/S SANJAY ADHIKARY | 17.13 | 17.09 | 99.75 | 60
13 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Restoration of road under Augmentation of Surface water based PWSS at Northern Sector Part II (Zone III/A)at Nakashipara block under Debagram Sub Division PHE DTE. | Assistant Engineer | Junior Engineer 1 | ORD/000689/2024-2025 | 1064/DSD | 30/12/2024 | 14/01/2025 | S.M.ENTERPRISE | 4.84 | 4.83 | 99.72 | 100
14 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | RESTORATION OF ROAD UNDER AUGMENTATION OF SURFACE WATER BASED PWSS AT NORTHERN SECTOR PART II (ZONE III/A) AT NAKASHIPARA BLOCK UNDER DEBAGRAM SUB DIVISION PHE DTE. | Assistant Engineer | Junior Engineer 1 | ORD/000785/2024-2025 | 111/DSD | 18/02/2025 | 05/03/2025 | S. M. S & CO | 4.85 | 2.55 | 52.58 | 100
15 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Dharmada Muragacha road from 0.000km to 0.800km for restoration of damaged carriageway due to laying of water supply pipe line on right hand side of the road by the PHED under Nadia Highway Division No-I in the district of Nadia during the year 2024-25. |  |  | BILL/00958/2024-2025 | BP-2024-025-378 | 18/03/2025 | 18/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 20.09 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11809 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000141/2025-2026 | 3447/ND | 23/07/2025 | 20/03/2026 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
Total | [13 empty] | 4959.27 | 336.67 | 6.79