## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Additional Route Survey, Design Drawing & DPR Preparation for ZONE 5B-A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000797/2021-2022 | 147/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 0.84 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 5B-B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000798/2021-2022 | 148/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.04 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 5B-A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000796/2021-2022 | 146/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.91 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 119/ND | 05/01/2023 | 05/01/2023 | Resource Division | 253.22 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Construction of Additional Boundary Wall ( 85.00 m Length ), Service Road and other related work for 1000 cum RCC elevated reservior of Surface Water Based Water Supply Scheme for Zone-V/B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000451/2024-2025 | 7246/ND | 12/12/2024 | 10/02/2025 | U-TURN CONSTRUCTION | 17.16 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 1000 m3. for Surface Water Based Piped Water Supply Scheme for Zone- V/ B (NORTHERN SECTOR, PART-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000368/2023-2024 | 4739/ND | 13/10/2023 | 12/12/2023 | U-TURN CONSTRUCTION | 35.83 | 0 | 0 | 65
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Reconstruction of Top Dome and other related work for 273 cum RCC elevated reservoir of Surface Water Based Water Supply Scheme for Zone-V /A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000190/2024-2025 | 6098/ND | 19/09/2024 | 18/12/2024 | BIDYUT KUMAR | 13.22 | 0 | 0 | 10
9 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 236/ND | 11/01/2024 | 11/01/2024 | Resource Division | 19.68 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000342/2023-2024 | 4527/ND | 04/10/2023 | 24/11/2025 | KINGS & CO. | 672.01 | 0 | 0 | 25
11 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Jack pushing & pipe crossing work at Jugpur Mouza under Northern Sector Part-II under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000002/2025-2026 | 1645/ND | 07/04/2025 | 06/07/2025 | MONDAL ENTERPRISE | 95.97 | 0 | 0 | 1
12 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11810 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 08/10/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
Total | [13 empty] | 1309.42 | 0 | 0