## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Name of Work : Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Baruipara W/S Scheme in Karimpur-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000368/2021-2022 | 289/TSD | 24/11/2021 | 24/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.82 | 100 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Baruipara to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000132/2022-2023 | 3798/ND | 02/09/2022 | 13/02/2026 | M/S S.S ENTERPRISE | 732.02 | 577.34 | 78.87 | 74
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 4307/ND | 29/09/2022 | 29/09/2022 | Resource Division | 41.46 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No. I,II III under Baruipara WS Scheme, Block Karimpur I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-13) | Assistant Engineer | Junior Engineer | ORD/000893/2022-2023 | 161-EMD | 06/01/2023 | 01/01/2025 | P.K. ENGINEERING | 22.81 | 0 | 0 | 100
5 | NADIA |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Baruipara W/S Scheme (T/W-I) , Karimpur-I Block under Nadia District, Central Drilling Division, P.H.E. Dte.(2ed Call) | Driller In Charge | Junior Engineer | ORD/000092/2023-2024 | 507/CDD | 01/06/2023 | 30/03/2024 | UNIVERSAL ENTERPRISES | 18.86 | 14.69 | 77.87 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1850/ND | 26/04/2023 | 26/04/2023 | Resource Division | 56.81 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 174 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Baruipara to accommodate FHTC within Karimpur-I block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000086/2024-2025 | 4192/ND | 31/07/2024 | 21/07/2026 | MONDAL ENTERPRISE | 381.95 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Construction Of Pump House (3.6x 3.0m) Including Sanitary Arrangement and consruction of Boundary wall at 4th Tube Well Site of Baruipara Water Supply Scheme Under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000751/2023-2024 | 1626/ND | 07/03/2024 | 22/11/2026 | BISHAL CONSTRUCTION | 10.94 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Laying pipe line for distribution system and rising main for Baruipara PWSS under augmentation of Baruipara PWSS under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000474/2024-2025 | 7262/ND | 13/12/2024 | 08/03/2026 | M/S S.S ENTERPRISE | 54.36 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Baruipara Ground Based Water Supply Scheme under Karimpur-I Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Baruipara at Karimpur-I Block by Augmentation of Ground Water based PWSS for Baruipara Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000638/2024-2025 | 7364/ND | 18/12/2024 | 16/02/2025 | M/S ARATI ENTERPRISE | 23.38 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Providing FHTC & Alied Pipelines and other Works for left out habitation under Karimpur -I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000792/2024-2025 | 7464/ND | 20/12/2024 | 20/03/2025 | APURBA MANDAL | 299.14 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-IV under Baruipara ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. 2024_PHED_664112_2 | Assistant Engineer | Junior Engineer | ORD/003002/2023-2024 | 924/EMD | 15/03/2024 | 14/04/2024 | P.K. ENTERPRISE | 7.36 | 4.51 | 61.27 | 60
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Quotation charges for new service connection and security deposit at Baruipara PH-IV under EMSD-III,Nadia |  |  | BILL/02256/2024-2025 | BP-182 | 13/12/2024 | 13/12/2024 | WBSEDCL KARIMPUR CCC | 3.86 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Additional pipeline for increasing Functionality in Basatipara, Mojlishpur and Borojangal villages through MANIFOLD under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM). | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer Karimpur- II Block | ORD/000158/2025-2026 | 3256/ND | 10/07/2025 | 03/09/2026 | GOPAL KIRTYANIYA | 15.51 | 0 | 0 | 20
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte. | SM/11815 | Augmentation | Laying of additional pipe lines and allied works to increase the functionality in Brojonathpur, Gandhina villages under Karimpur-I Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer Karimpur- II Block | ORD/000328/2025-2026 | 4685/4533/P-3/ND | 09/10/2025 | 07/04/2026 | JOY HIND TUBEWELL'S | 46.3 | 0 | 0 | 40
Total | [13 empty] | 1719.59 | 601.36 | 34.97