## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11834 | Augmentation | Schedule for Route Survey, Design Drawing & DPR Preparation for ZONE 7B of Surface Water based Piped water Supply Scheme for Northern Sector Part-I in Kaliganj Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000779/2021-2022 | 129/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.82 | 4.81 | 99.86 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11834 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 106/ND | 05/01/2023 | 05/01/2023 | Resource Division | 168.02 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11834 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 25/07/2026 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 685.36 | 4.17 | 47
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11834 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 17/05/2025 | UMWELT ENGINEER PVT LTD | 225.66 | 18.99 | 8.42 | 75
Total | [13 empty] | 16842.67 | 709.16 | 4.21