## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 1/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000785/2021-2022 | 135/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.91 | 3.8 | 97.11 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 91/ND | 05/01/2023 | 05/01/2023 | Resource Division | 64.78 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 137 cum. for Providing FHTC (Functional Household Tap Connection) for Zone -I/A (Northern Sector, Part-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte.¿ | Assistant Engineer | Junior Engineer 3 | ORD/000260/2023-2024 | 3998/ND | 07/09/2023 | 06/11/2023 | M/S ARATI ENTERPRISE | 13.1 | 13.09 | 99.94 | 65
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 235/ND | 11/01/2024 | 11/01/2024 | Resource Division | 3.79 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- I/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000311/2023-2024 | 4281/ND | 21/09/2023 | 24/06/2025 | PRASUN ENTERPRISE | 268.05 | 70.56 | 26.32 | 25
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Construction of OHR, repair and renovation of staff room, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-I / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. [SM/11836]. | Assistant Engineer | Junior Engineer 3 | ORD/000430/2023-2024 | 5556/ND | 12/12/2023 | 10/12/2025 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 150.28 | 0 | 0 | 5
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11836 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000141/2025-2026 | 3447/ND | 23/07/2025 | 20/11/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
Total | [13 empty] | 1333.23 | 90.24 | 6.77