## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000792/2021-2022 | 142/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 3.94 | 3.94 | 99.98 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 96/ND | 05/01/2023 | 05/01/2023 | Resource Division | 297.03 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. for Providing FHTC (Functional Household Tap Connection) for Zone -IV/A (NORTHERN SECTOR, PART-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000265/2023-2024 | 4001/ND | 07/09/2023 | 06/11/2023 | JOY HIND TUBEWELL'S | 33.19 | 0 | 0 | 45
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 244/ND | 11/01/2024 | 11/01/2024 | Resource Division | 7.83 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 25/03/2026 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 393.56 | 16.22 | 50
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2026 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11840 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 08/10/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
Total | [13 empty] | 4371.36 | 397.5 | 9.09