## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 4B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000793/2021-2022 | 143/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.63 | 3.91 | 84.34 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 123/ND | 05/01/2023 | 05/01/2023 | Resource Division | 114.87 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 242/ND | 11/01/2024 | 11/01/2024 | Resource Division | 12.52 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 26/09/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 175.61 | 7.24 | 50
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11841]. | Assistant Engineer | Junior Engineer 3 | ORD/000454/2023-2024 | 6152/ND | 26/12/2023 | 23/12/2025 | SATYABRATA CHAKRABORTY | 233.13 | 11.7 | 5.02 | 5
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2025 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11841 | Augmentation | Construction of Bituminous Approch Road for GLR site at Surface water based water supply Scheme under Northern Sector Part II at Nakashipara Block under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000165/2025-2026 | 3260/ND | 10/07/2025 | 08/10/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 95.58 | 0 | 0 | 5
Total | [13 empty] | 4491.48 | 192.62 | 4.29