## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11845 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 7/A of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000802/2021-2022 | 152/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.47 | 4.44 | 99.13 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11845 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2022-2023 | 78/ND | 05/01/2023 | 05/01/2023 | Resource Division | 168.95 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11845 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 241/ND | 11/01/2024 | 11/01/2024 | Resource Division | 6.45 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11845 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/A (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000309/2023-2024 | 4279/ND | 21/09/2023 | 20/06/2025 | MINTU CHAKRABORTY | 476.23 | 178.65 | 37.51 | 24
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11845 | Augmentation | Laying of additional upvc pipeline and installation of sluice valves at Zone -7A of Surface water based water supply scheme Northern Sector in Nadia District, Part- II under Debagram Sub- Division undrer Nadia Division ,PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000007/2024-2025 | 3261/ND | 10/06/2024 | 08/06/2025 | MINTU CHAKRABORTY | 96.03 | 0 | 0 | 4
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/A (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/11845 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum. For Providing FHTC (Functional Household Tap Connection) for Zone VII/A (NORTHERN SECTOR PART-II) Water Supply Scheme in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000261/2023-2024 | 4005/ND | 07/09/2023 | 28/02/2025 | TARUN KUMAR BHATTACHARYA | 43.67 | 0 | 0 | 1
Total | [13 empty] | 795.81 | 183.09 | 23.01