## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11871 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000187/2022-2023 | 142/ND | 06/01/2023 | 06/01/2023 | Resource Division | 27.61 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11871 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1852/ND | 26/04/2023 | 26/04/2023 | Resource Division | 22.01 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11871 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 2324/ND | 29/05/2023 | 29/05/2023 | Resource Division | 0.92 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11871 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Karimpur Jalangi Zone X-A to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000344/2022-2023 | 254/ND | 16/01/2023 | 05/01/2025 | SANJUKTA ENGINEERS | 157.12 | 0 | 0 | 98
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(A) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11871 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Karimpur Jalangi Zone-X (A) Ground Based Water Supply Scheme under Karimpur-II Block under Nadia Division,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Karimpur Jalangi Zone-X (A) at Karimpur-II Block by Augmentation of Ground Water based PWSS for Karimpur Jalangi Zone-X (A) Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000740/2024-2025 | 418/ND | 27/01/2025 | 23/03/2026 | S.B.CONSTRUCTION | 23.54 | 0 | 0 | 50
Total | [13 empty] | 231.21 | 0 | 0