## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11873 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under NARAYANPUR W/S Scheme, Block- Karimpur II , Dist. - Nadia. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 1581/EMD | 24/04/2023 | 24/05/2023 | CHANDIMATA ELECTRICALS | 15.43 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1906/ND | 27/04/2023 | 27/04/2023 | Resource Division | 18.64 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11873 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 2315/ND | 29/05/2023 | 29/05/2023 | Resource Division | 0.92 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED NARAYANPUR PWSS PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/11873 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Proposed Augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 200 Cum Capacity 20 Mtr. height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of one no. 200 Cum OHR of Staging Height 20 Mtr. for Augmentation of Ground Based Water Supply Scheme at Narayanpur to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000437/2022-2023 | 966/ND | 09/03/2023 | 09/03/2026 | M/S S.S ENTERPRISE | 759.95 | 0 | 0 | 55
Total | [13 empty] | 794.95 | 0 | 0