## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Construction of barbed wire fencing with concrete pillars at Hanspukuria Zone-II (2nd T.W). water supply scheme( New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . | Assistant Engineer |  | ORD/000582/2022-2023 | 931/TSD | 14/03/2023 | 21/03/2023 | PRABIR KUMAR ROY | 0.46 | 0.46 | 100 | 0
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Hanspukuria W/S Scheme in Tehatta-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000451/2021-2022 | 298/TSD | 24/11/2021 | 24/12/2021 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.07 | 4.07 | 100 | 100
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000181/2022-2023 | 153/ND | 06/01/2023 | 06/01/2023 | Resource Division | 154.79 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000197/2022-2023 | 1026/ND | 13/03/2023 | 13/03/2023 | Resource Division | 1.39 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 2310/ND | 29/05/2023 | 29/05/2023 | Resource Division | 13.8 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Construction Of Pump House (5.4m X 3.6m) & (3.6m X 3.0m) Including Sanitary Arrangement At Head Work Site & 2nd tube well Site and construction of Boundary wall at Head works site & 2nd tube well site of Hanspukuria Zone - II Ground water based water supply scheme under Tehatta Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000756/2023-2024 | 1630/ND | 07/03/2024 | 03/09/2024 | J.P. CONSTRUCTION & SUPPLIERS | 34.04 | 14.57 | 42.81 | 65
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hasnpukuria Zone-I to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000261/2024-2025 | 4701/ND | 29/08/2024 | 25/02/2025 | MONDAL PRECISION PRIVATE LIMITED | 181.86 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Repairing and renovation of Elevated Reservoir , Pump House ,boundary wall of ground based piped water supply scheme for Hanspukuria Zone-I water supply scheme under Tehatta Sub Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000307/2024-2025 | 6836/ND | 12/11/2024 | 10/02/2025 | BUDDHADEV MONDAL | 32.88 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Construction of barbed wire fencing with concrete pillars at Hanspukuria Zone-II water supply scheme 1st T.W. H.W.Site (New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . |  | Junior Engineer 1,Junior Engineer 2 | ORD/000728/2023-2024 | 1117/TSD | 21/02/2024 | 28/02/2024 | PRABIR KUMAR ROY | 2.13 | 2.05 | 96.16 | 100
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Headwork site , Hanspukuria Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000662/2023-2024 | 1097/ND | 19/02/2024 | 20/03/2024 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 17.39 | 12.21 | 70.21 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 3503/ND | 24/06/2024 | 24/06/2024 | Resource Division | 12.39 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Quotation for New service connection charges and security deposit for Hanspukuria 2nd T/W. |  |  | BILL/02156/2024-2025 | BP-172-24-25 | 05/12/2024 | 05/12/2024 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 3.02 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Quotation charges and security deposit for new power connection at Hanspukuria (Zone-II) head worksite under Eastern Mechanical Subdivision-III, Nadia |  |  | BILL/02255/2024-2025 | BP-193-24-25 | 16/12/2024 | 16/12/2024 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 9.18 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Ground Based Water Supply Scheme at Hanspukuria Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000311/2022-2023 | 5351/ND | 22/12/2022 | 22/12/2024 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 203.73 | 177.3 | 87.02 | 95
15 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure all complete, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete, Construction of 300 cum capacity 20 mtr. height RCC over head reservoir (with pile foundation), pipe connection and cost of pipes, specials. and Soil investigation for construction of one No. 300 Cum OHR of staging height 20 mtr. for Augmentation of Ground Based Water Supply Scheme at Hanspukuria Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000392/2022-2023 | 480/ND | 02/02/2023 | 02/02/2025 | M/S DIPAK ENTERPRISE, GHOSH PARA,WORD NO.-4, KALYANI, NADIA-741235 WEST BENGAL | 291.32 | 121.61 | 41.75 | 65
16 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Hanspukuria Zone-I Ground Based Water Supply Scheme under Tehatta-II Block under Nadia Division, P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanspukuria Zone-I at Tehatta-II Block by Augmentation of Ground Water based PWSS for Hanspukuria Zone-I Water Supply Schemes under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000625/2024-2025 | 7358/ND | 18/12/2024 | 16/02/2025 | SAHA CONSTRUCTION & CO | 20.43 | 0 | 0 | 0
17 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Hasnpukuria Zone-II to accommodate FHTC within Tehatta-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000260/2024-2025 | 4700/ND | 29/08/2024 | 24/08/2025 | MONDAL PRECISION PRIVATE LIMITED | 181.28 | 0 | 0 | 0
18 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejumination Tube Well and New Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III , IV Zone-I & Pump House No.-I ,II (Zone-II) under Hanspukuria ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. (SM/11918) | Assistant Engineer | Junior Engineer | ORD/001467/2024-2025 | 238/EMD | 06/02/2025 | 08/03/2025 | DEY ENTERPRISE | 72.07 | 0 | 0 | 25
19 | NADIA |  | Eastern Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia | SM/11918 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Hanspukuria ground water based water supply scheme under Block_ Tehatta-II Dist. - Nadia under EMD, PHE Dte. SM/11918 | Assistant Engineer |  | ORD/000176/2025-2026 | 1109/EMD | 04/06/2025 | 02/09/2025 | ANJAN ENTERPRISE | 20.8 | 0 | 0 | 0
Total | [13 empty] | 1257.05 | 332.27 | 26.43