## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Palsunda W/S Scheme in Tehatta-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000393/2021-2022 | 308/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 3.08 | 2.95 | 95.77 | 100
2 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1908/ND | 27/04/2023 | 27/04/2023 | Resource Division | 144.56 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 2300/ND | 29/05/2023 | 29/05/2023 | Resource Division | 31.86 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 120 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Polsunda to accommodate FHTC within Tehatta-II block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000085/2024-2025 | 4191/ND | 31/07/2024 | 27/01/2025 | MONDAL ENTERPRISE | 297.09 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Making barbed wire fencing with concrete pillars at Polsunda water supply scheme (New Land)H.W.Site under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . |  | Junior Engineer 1,Junior Engineer 2 | ORD/000724/2023-2024 | 1116/TSD | 21/02/2024 | 28/02/2024 | PRABIR KUMAR ROY | 2.94 | 2.84 | 96.5 | 100
6 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Laying of 63mm dia UPVC Pipe line for Revision of drawing to accommodate FHTC & Construction of Jhama Bats Road for the approach way to headwork site of Palsunda water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000048/2024-2025 | 3454/ND | 20/06/2024 | 19/08/2024 | MONDAL ENTERPRISE | 54.5 | 54.32 | 99.67 | 98
7 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Lying distribution system for providing FHTC at Palsunda Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000049/2024-2025 | 3455/ND | 20/06/2024 | 18/09/2024 | MONDAL ENTERPRISE | 96.94 | 25.86 | 26.68 | 100
8 | NADIA |  | Eastern Mechanical | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Quotation charges and security deposit for new power connection at Palsunda-III head worksite under Eastern Mechanical Subdivision-III, Nadia |  |  | BILL/02261/2024-2025 | BP-183 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (PANCHDHARA ABHAYNAGAR C.C.C) | 7.79 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accommodate FHTC under KARIMPUR JALANGI(Z-8) W/S Scheme, Block- Karimpur II, PALSONDHA W/S Scheme, Block- Tehatta II, & MAIDANPUR W/S Scheme, Block- Chapra, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/001923/2022-2023 | 1179/EMD | 21/03/2023 | 16/10/2025 | CREATIVE WATER & PROCESS TECHNOLOGIES PVT. LTD. | 77.9 | 0 | 0 | 85
10 | NADIA |  | Nadia Division | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District. | SM/11919 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 650 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Palsunda to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000014/2023-2024 | 1720/ND | 17/04/2023 | 17/04/2026 | MONDAL ENTERPRISE, MASJID BARI ROAD,UTTAR BALURIA, P.O.NABAPALLY, P.S. BARASAT NORTH 24 PGS. | 593.41 | 339.64 | 57.23 | 45
Total | [13 empty] | 1310.06 | 425.6 | 32.49