## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Udaypur W/S Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000438/2021-2022 | 1058/RSD | 02/12/2021 | 01/01/2022 | HORIZEN | 3.35 | 2.95 | 88.03 | 100
2 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Udaypur W/S Scheme (T/W-I),Santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 512/CDD | 01/06/2023 | 01/07/2023 | UTTAM KUMAR CHATTERJEE | 18.88 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1863/ND | 26/04/2023 | 26/04/2023 | Resource Division | 46.68 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 3543/ND | 11/08/2023 | 11/08/2023 | Resource Division | 75.5 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Udaypur piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000174/2024-2025 | 1137/RSD | 11/09/2024 | 26/10/2024 | MAA SARADA CONSTRUCTION | 1.9 | 1.76 | 92.83 | 100
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000136/2023-2024 | 254/ND | 11/01/2024 | 11/01/2024 | Resource Division | 12.33 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Construction of Pump house and Boundary wall at head work site in related to augmentation of Ground Water Based Piped Water Supply Scheme for Udaypur Water Supply scheme under Santipur Block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000588/2023-2024 | 845/ND | 06/02/2024 | 02/10/2025 | S.M. CONSTRUCTION | 24.18 | 0 | 0 | 70
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under Augmentation of Udaypur PWSS. | Assistant Engineer | Junior Engineer 3 | ORD/000815/2024-2025 | 206/RSD | 06/02/2025 | 23/03/2025 | GITARANI ENTERPRISE | 3.19 | 0 | 0 | 100
9 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Udaypur ground water based water supply scheme under Block_Santipur Dist. - Nadia under EMD, PHE Dte.(SM/11925) | Assistant Engineer |  | ORD/000190/2025-2026 | 1128/EMD | 04/06/2025 | 02/09/2025 | SHIVAM ENTERPRISE | 24.59 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA | SM/11925 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 307.58 | 4.71 | 1.53