## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Laying of distribution system including specials, valves & pipe supporting structure all complete and providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-I to accommodate FHTC within Ranaghat-II Dev. block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000151/2022-2023 | 4238/ND | 28/09/2022 | 27/02/2025 | SUPRITI ENTERPRISE | 533.43 | 488.8 | 91.63 | 100
2 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 4931/ND | 25/11/2022 | 25/11/2022 | Resource Division | 166.85 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Repairing of PH-III and Construction of Sanitary arrangement under augmentation of Naserkuli Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000387/2024-2025 | 1423/RSD | 19/11/2024 | 03/01/2025 | M. ENTERPRISE | 2.14 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Repairing of PH-II and Construction of Sanitary arrangement under augmentation of Naserkuli Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000386/2024-2025 | 1422/RSD | 19/11/2024 | 03/01/2025 | AVIRUP CONSTRUCTION | 2.14 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Repairing of PH-IV and Construction of Sanitary arrangement under augmentation of Naserkuli Zone-I under Ranaghat Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000388/2024-2025 | 1424/RSD | 19/11/2024 | 03/01/2025 | PURBA SERVICES | 2.14 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-1 site at Naserkuli Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000223/2024-2025 | 1187/RSD | 25/09/2024 | 09/12/2024 | M. ENTERPRISE | 4.44 | 1.16 | 26.09 | 100
7 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Naserkuli Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000308/2024-2025 | 1277(A)RSD | 04/10/2024 | 18/11/2024 | M/S SANYAL ENTERPRISE | 1.9 | 1.08 | 56.91 | 100
8 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | NH-34 to Ravenberia via Payradanga Rly. Stn. Road from 0.00 km to 1.103 km (Both Side) - Restoration work arising out of damage of hard shoulder for laying of UPVC & DI pipeline under PHE Nadia Division, pHE Dte. under Nadia Highway Division No -II, in the District of Nadia during the year 2023-2024. |  |  | BILL/00628/2024-2025 | 361/PFMS | 12/12/2024 | 12/12/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-II, P.W. (ROADS) DIRECTORATE | 5 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | urgent repairing work of pipe line damaged by N.H. during construction of surface drain at nearby Begopara-Coopers approach road within Ranaghat-I block under Ranaghat Sub-Division, Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000799/2024-2025 | 89/RSD | 14/01/2025 | 28/02/2025 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 2.3 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Deposition of balance fund related to restoration work of NH-34 to Ravanberia vi Payradanga Rly. Station Road fram Ch. 0.00 km to Ch. 1.103 km (LHS & RHS) under Nadia Highway Division No-II, due to laying of PHED pipe line. |  |  | BILL/00119/2025-2026 |  | 28/04/2025 | 28/04/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-II, P.W. (ROADS) DIRECTORATE | 9.95 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Augmentation of Ground Water Based Piped Water Supply Scheme for NASERKHULI ZONE-I to Accommodate FHTC in Ranaghat-II Block of Nadia District under Nadia Division, P.H.E. Dte | SM/11978 | Augmentation | Laying of distribution system including specials, valves & pipe supporting structure all complete and providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (Schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of ground based water supply scheme at Naserkhuli Zone-I to accommodate FHTC within Ranaghat-II Dev. block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. |  |  | BILL/01138/2024-2025 | BP-2024-025-480 | 28/03/2025 | 28/03/2025 | SUPRITI ENTERPRISE | 25.93 | 0 | 0 | 0
Total | [13 empty] | 853.19 | 491.03 | 57.55