## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-II | Nadia Division | Mini Piped Water Supply Scheme at Uttar Bishnupur Village, Block- Ranaghat-II, District- Nadia. | SM/12005 | New | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for Mini Piped Water Supply Scheme Gazna (Part) (100 Households) to accommodate FHTC in Hanskhali block & Providing FHTC and allied works for- Ground Water Based Mini Piped Water Supply Scheme in Arsenic affected area at Uttar Bishnupur, Block : -Ranaghat-II, Nadia District under Nadia Division P.H.E Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer 4 | ORD/000090/2023-2024 | 3024/ND | 14/07/2023 | 14/07/2024 | ABDUL ALIM MONDAL | 79.83 | 0 | 0 | 78
2 | NADIA | Ranaghat-II | Nadia Division | Mini Piped Water Supply Scheme at Uttar Bishnupur Village, Block- Ranaghat-II, District- Nadia. | SM/12005 | New | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 271/ND | 11/01/2024 | 11/01/2024 | Resource Division | 0.6 | 0 | 0 | 0
3 | NADIA | Ranaghat-II | Nadia Division | Mini Piped Water Supply Scheme at Uttar Bishnupur Village, Block- Ranaghat-II, District- Nadia. | SM/12005 | New | New Service Connection charges for Uttar Bishunupur Mini Piped water supply scheme |  |  | BILL/00416/2024-2025 | 243/PFMS | 13/09/2024 | 13/09/2024 | W.B.S.E.D.C.L (GROUP ARANGHATA C.C.C) | 0.21 | 0 | 0 | 0
Total | [13 empty] | 80.64 | 0 | 0