## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Survey , Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household under Tungi W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Sl.No. 01) | Assistant Engineer |  | ORD/000340/2021-2022 | 904/KSD | 29/11/2021 | 14/12/2021 | HORIZEN | 3.86 | 2.74 | 71.04 | 100
2 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works etc. rejuvenation to Accomodate FHTC at Pump House No.I and II under Tungi WS Scheme, Block Krishnaganj, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-11) |  |  | ORD/000892/2022-2023 | 160/EMD | 06/01/2023 | 05/02/2023 | KUNDU ELECTRICAL ENTERPRISE | 21.11 | 19.47 | 92.22 | 10
3 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Supplementary works to completion of ongoing FHTC-related work at PH-I & II of Tungi W/S Scheme (Block - Krishnaganj), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001391/2023-2024 | 599/EMSD-II | 22/08/2023 | 06/09/2023 | KUNDU ELECTRICAL ENTERPRISE | 0.87 | 0.82 | 94.37 | 100
4 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 117/ND | 05/01/2023 | 05/01/2023 | Resource Division | 28.88 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Laying of Distribution System including specials & valves, pipe supporting structure all complete based on actual., proposed augmentation of Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete. , Construction of R.C.C. Elevated Reservoir of 550 Cum capacity(including pile foundation) , Soil investigation for construction of one No. 550 Cum OHR, Construction of 1 No. Pump House at proposed Head Work site and Construction of boundary wall with gate for Tungi Water Supply Scheme in Krishnagunj Block of Nadia District under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000202/2023-2024 | 3520/ND | 10/08/2023 | 01/01/2026 | MANGES INDUSTRIAL CORPORATION | 494.78 | 44.53 | 9 | 25
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
7 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Tungi W/S Scheme (TW-I) , Krishanjganj Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000131/2023-2024 | 1232/CDD | 04/09/2023 | 01/12/2024 | PADMA ENGINEERING & CO. | 18.88 | 13.24 | 70.12 | 100
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 263/ND | 11/01/2024 | 11/01/2024 | Resource Division | 35.85 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | WBSEDCL Quotation for New Service Connection to the newly Head Work Site under TUNGI W/S Scheme in Krishnaganj Block, P.H.E. Dte., Dist.- Nadia. (Application No. 3004956363) |  |  | BILL/01890/2024-2025 | BP-167-24-25 | 25/11/2024 | 25/11/2024 | W.B.S.E.D.C.LTD (KRISHNAGANJ C.C.C) | 4.96 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 cum/hr at Tungi water supply scheme including 3 Months Trial Run & 3 Years O&M within krishnaganj block under Krishnagar Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000722/2023-2024 | 1304/ND | 23/02/2024 | 16/08/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 300.57 | 0 | 0 | 50
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Additional Laying of Distribution System and allied works for Water Supply Scheme under Krishnaganj Block under Krishnagar Sub Division, Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000696/2024-2025 | 91/ND | 07/01/2025 | 21/02/2025 | A.P. POWER & CONCRETE | 22.87 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Including pile foundation), pipe connection and cost of pipes, specials for Ref. Drawing No.PC-I/OHR/16/2012 (Sheet No.1&2) and Laying of additional UPVC Pipeline in connection to the Ground Based piped water supply scheme at Tungi to accommodate FHTC within Krishnaganj block under Krishnanagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000385/2024-2025 | 7091/ND | 05/12/2024 | 05/12/2025 | MANGES INDUSTRIAL CORPORATION | 334.65 | 0 | 0 | 5
13 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA | SM/12363 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Tungi ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte. SM/12363 | Assistant Engineer | Junior Engineer | ORD/000367/2025-2026 | 1124/EMD | 04/06/2025 | 02/09/2025 | SHREE BISHNU CONSTRUCTION | 31.04 | 0 | 0 | 0
Total | [13 empty] | 1395.28 | 83.6 | 5.99