## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 98/ND | 05/01/2023 | 05/01/2023 | Resource Division | 149.04 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 237/ND | 11/01/2024 | 11/01/2024 | Resource Division | 23.66 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Restoration work of road damage due to laying pipe line under ¿NJJM¿ Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Arbetai ¿ Sahapara Road from 9.80 kmp to 11.88 kmp of Krishnagar Sub-Division-I under Nadia Highway Division-I in the district Nadia during the year 2024-2025. |  |  | BILL/00249/2024-2025 |  | 26/07/2024 | 26/07/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 12.59 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | RESTORATION OF ROAD FLANK OF ARBETAI SAHAPARA ROAD FROM CH. 0.00 KM TO 9.80 KMP. |  |  | BILL/01489/2023-2024 | 601/PFMS | 14/03/2024 | 14/03/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 28.69 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Restoration work of road damage due to laying pipe line under ¿NJJM¿ Project in Nakashipara Block of Nadia District under Nadia Division, PHE Dept. of Arbetai ¿ Sahapara Road from 9.80 kmp to 11.88 kmp of Krishnagar Sub-Division-I under Nadia Highway Division-I in the district Nadia during the year 2024-2025. |  |  | BILL/00343/2024-2025 | 148/PFMS | 28/08/2024 | 28/08/2024 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 6.3 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- V/C (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000343/2023-2024 | 4528/ND | 04/10/2023 | 18/03/2026 | M/S DIPAK ENTERPRISE | 645.85 | 386.75 | 59.88 | 50
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12373 | Augmentation | Construction of OHR, staff room, chlorine room, service road and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-V / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12373]. | Assistant Engineer | Junior Engineer 3 | ORD/000471/2023-2024 | 148/ND | 09/01/2024 | 07/01/2026 | MINTU CHAKRABORTY | 252.66 | 0 | 0 | 10
Total | [13 empty] | 1215.75 | 389.55 | 32.04