## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Route Survey, Design Drawing & DPR Preparation for ZONE 6/B of Surface Water based Piped water Supply Scheme for Northern Sector Part-II in Nakashipara Block under Debagram Sub Division, PHE Dte. | Assistant Engineer |  | ORD/000801/2021-2022 | 151/DSD | 17/03/2022 | 16/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.51 | 4.51 | 100 | 100
2 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 100/ND | 05/01/2023 | 05/01/2023 | Resource Division | 358.26 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 2.8 | 2.89 | 40
4 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Restoration of Muragacha Ghosh Para to Dharmada Hospital via Mirpur Kachkuli under (RIDF XXVIII) |  |  | BILL/00532/2024-2025 | 320/PFMS | 05/10/2024 | 05/10/2024 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 16.91 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | RESTORATION OF L071-BTHUADHRI PHE TO DAFADR PARA (BIL KUMARI) under Package No. WB/14/227 |  |  | BILL/00512/2024-2025 | 303/PFMS | 02/10/2024 | 02/10/2024 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 17.55 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Restoration of T 09 - Barabigha to fakir Danga to Arbetai under Package no. WB 14-ADB37. |  |  | BILL/00448/2024-2025 | 261/PFMS | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 14.21 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 26/09/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 255.77 | 10.54 | 50
8 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Construction of OHR, staff room, chlorine room, service road, boundary wall and restoration of bituminous road, land improvement etc. of Surface Water Based Water Supply Scheme for Zone-VI / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/12374]. | Assistant Engineer | Junior Engineer 2 | ORD/000479/2023-2024 | 211/ND | 10/01/2024 | 09/01/2026 | SARKAR CONSTRUCTION | 348.98 | 1.7 | 0.49 | 10
9 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 16/03/2025 | BIBHAS PAL | 96.01 | 5.92 | 6.17 | 30
10 | NADIA |  | Nadia Division | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/12374 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2025 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
Total | [13 empty] | 4887.19 | 270.7 | 5.54