## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities | SM/12848 | Support-IEC | Making of Documentary film on "Jal Swapno Project" achievements in Nadia District. | Assistant Engineer |  | ORD/000078/2022-2023 | 3299/ND | 27/07/2022 | 26/08/2022 | SPAN COMMUNICATIONS | 8.5 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities | SM/12848 | Support-IEC | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities | Assistant Engineer | Junior Engineer 2 | ORD/000171/2023-2024 | 3272/ND | 31/07/2023 | 31/01/2024 | IMAGIN | 54.33 | 0 | 0 | 91
3 | NADIA |  | Nadia Division | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities | SM/12848 | Support-IEC | Information Education Communication (IEC) Activities related to judicious & safe use of drinking water, water conservation, water quality issues Under Jal Jeevan Mission (JJM) Support Activities. [Phase-II] | Assistant Engineer | Junior Engineer 2 | ORD/000661/2023-2024 | 6161/ND | 26/12/2023 | 26/06/2024 | IMAGIN | 74.48 | 0 | 0 | 100
Total | [13 empty] | 137.31 | 0 | 0