## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Dogachhi W/S Scheme in Karimpur-II Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000397/2021-2022 | 312/TSD | 24/11/2021 | 24/12/2021 | RADIANT | 3.4 | 3.4 | 100 | 100
2 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DOGACHI (ZONE-I) W/S SCH, KARIMPUR-II BLOCK, UNDER NADIA DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000376/2022-2023 | 1196/CDD | 11/11/2022 | 11/12/2022 | M/S SAIKAT ENTERPRISE | 10.22 | 7.76 | 75.97 | 0
3 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Supply and delivery of Pea size Gravels at site for construction of Tube Well (300mm X 200mm X 150 Mtrs. Depth) by utilising Departmental Machineries for Dogachi Zone-I W/S Scheme, Karimpur-II Block under Nadia District under CMSD-II(D), CDD, PHE, Dte. | Driller In Charge | Junior Engineer | ORD/000485/2022-2023 | 535/CMSD-II | 02/12/2022 | 17/12/2023 | M/S SAIKAT ENTERPRISE | 0.98 | 0.67 | 68.47 | 100
4 | NADIA |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | ADDITIONAL TRANSPORTATION OF DEPARTMENTAL RIG UNIT NO. SUPER RR WITH COMPRESSOR AND PUMP UNIT FROM DOGACHI UNDERCMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000506/2022-2023 | 562/CMSD-II | 30/12/2022 | 09/01/2023 | PADMA ENGINEERING & CO. | 0.75 | 0.75 | 100 | 100
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Construction of barbed wire fencing with concrete pillars at Dogachhi-Zone-II. water supply scheme(Sahebpara) (New Land 2nd T.W) under Tehatta Sub-Division PHE Dte. in JJM project . | Assistant Engineer |  | ORD/000584/2022-2023 | 932/1/TSD | 14/03/2023 | 21/03/2023 | NIVEDITA CONSTRUCTION | 0.71 | 0.71 | 100 | 0
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 300 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dogachhi Zone-II to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer Nabadwip Block | ORD/000539/2022-2023 | 1398/ND | 29/03/2023 | 31/12/2025 | SUBHASH BOSE | 312.69 | 179.99 | 57.56 | 20
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed augmentation of Rising Main system, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 350 Cum Capacity 20 Mtr. Height RCC Over Head Reservoir (Excluding Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for construction of OHR all complete for Augmentation of Ground Based Water Supply Scheme at Dogachhi Zone-I to accommodate FHTC under Tehatta Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000012/2023-2024 | 1719/ND | 17/04/2023 | 31/12/2026 | JOY HIND TUBEWELL'S | 441.71 | 320.61 | 72.58 | 70
8 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1903/ND | 27/04/2023 | 27/04/2023 | Resource Division | 92.46 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 2321/ND | 29/05/2023 | 29/05/2023 | Resource Division | 34.62 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 3641/ND | 16/08/2023 | 16/08/2023 | Resource Division | 12.39 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at 2nd Tubewell site, Dogachhi Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000344/2024-2025 | 4573/ND | 21/08/2024 | 20/09/2024 | ZEST INFRACON | 17.4 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 77 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE DTE. | Assistant Engineer | Junior Engineer 1 | ORD/000154/2024-2025 | 4349/ND | 07/08/2024 | 02/08/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 218.56 | 0 | 0 | 70
13 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Laying of Distribution System at Dogachi Mouza for Dogachi Piped Water Supply Scheme Zone-II in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi PWSS to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer Nabadwip Block | ORD/000067/2024-2025 | 3990/ND | 22/07/2024 | 20/09/2024 | SUNIL KUMAR DATTA | 20.07 | 4.12 | 20.51 | 100
14 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Sinking of 01 nos Tubewell 300 x 200 mm dia and 200 mtr. Deep Tubewell by Direct Rotary Rig Method, having 300 mm dia 48 mtr. long PVC Housing Pipe & 200 mm.dia Well Pipe & Deep well Screen (RDS strainer) at Headwork site, Dogachhi Zone-II PWSS Water Supply Scheme under Tehatta Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000343/2024-2025 | 4574/ND | 21/08/2024 | 20/09/2024 | ZEST INFRACON | 17.4 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 51 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-II to accommodate FHTC within Karimpur-II block under Tehatta Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer Nabadwip Block | ORD/000826/2024-2025 | 5078/ND | 17/09/2024 | 12/09/2025 | MANGES INDUSTRIAL CORPORATION | 183.53 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | (Horizontal) boring and Drum Sheet Walling for Dogachi Piped Water Supply Scheme Zone-I at Karimpur-II, Block at Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000841/2023-2024 | 370/KlySD-I | 01/03/2024 | 01/04/2024 | JOY HIND TUBEWELL'S | 13.42 | 13.4 | 99.83 | 100
17 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Construction of barbed wire fencing with concrete pillars at Dogachhi Zone-II (H/W) Site. water supply scheme(Sahebpara New Land) under Tehatta Sub-Division under Nadia Division PHE Dte. in JJM project . |  | Junior Engineer 1,Junior Engineer 2 | ORD/000729/2023-2024 | 1118/TSD | 21/02/2024 | 28/02/2024 | NIVEDITA CONSTRUCTION | 1.71 | 1.6 | 93.48 | 100
18 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangement At H.W Site & another Pump House (3.6m X 3.0m) Including Sanitary Arrangemet At 2nd Tube well site at Dogachi zone II Water Supply Scheme Under Kalyani Sub Division I PHE Dte.) | Assistant Engineer | Junior Engineer 2 | ORD/000028/2024-2025 | 3423/ND | 19/06/2024 | 17/09/2024 | NIVEDITA CONSTRUCTION | 12.43 | 12.39 | 99.66 | 100
19 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Laying of Distribution System for Dogachi Piped Water Supply Scheme Zone-I in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000071/2024-2025 | 3991/ND | 22/07/2024 | 13/12/2024 | MALI CONSTRUCTION | 40.01 | 27.18 | 67.93 | 70
20 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Repairing and renovation of existing pump house cum chlorin room and allied work at head work site,2nd tube well site under Dogachi Zone-I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000677/2024-2025 | 7446/ND | 20/12/2024 | 18/02/2025 | TOTAN DAS | 14.49 | 0 | 0 | 100
21 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube well and Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-Z-I & II under Dogachi ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. [SM/13039] | Assistant Engineer |  | ORD/000022/2025-2026 | 692/EMD | 04/04/2025 | 04/05/2025 | PADMA ENGINEERING CO. | 50.38 | 0 | 0 | 0
22 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I and II of Z-I & Z-II under DOGACHI ground water based water supply scheme under Block_ KARIMPUR-II Dist. - Nadia under EMD, PHE Dte. SM/13039 | Assistant Engineer |  | ORD/000184/2025-2026 | 1121/EMD | 04/06/2025 | 02/09/2025 | A.G ENTERPRISE. | 41.59 | 0 | 0 | 0
23 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Laying of Distribution System and allied works for Dogachi Piped Water Supply Scheme Zone-I in connection with Augmentation of Ground Based Water Supply Scheme at Dogachi Zone-I to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000005/2025-2026 | 1663/ND | 08/04/2025 | 07/06/2025 | MALI CONSTRUCTION | 26.66 | 0 | 0 | 0
24 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Quotation charges and security deposit for new service connection at PH-II of Karimpur Dogachi (Zone-II) W/S Scheme under EMSD-III,PHE Dte., Nadia. |  |  | BILL/02511/2024-2025 | BP-226-24-25 | 22/01/2025 | 22/01/2025 | WBSEDCL KARIMPUR CCC | 6.31 | 0 | 0 | 0
25 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13039 | Augmentation | Quotation charges and security deposit for new service connection at Karimpur Dogachi (Zone-II) PH-I (Block-Karimpur-II) under Easter Mechanical Division. |  |  | BILL/03118/2024-2025 | BP-279 | 26/03/2025 | 26/03/2025 | WBSEDCL KARIMPUR CCC | 9.87 | 0 | 0 | 0
Total | [13 empty] | 1583.76 | 572.58 | 36.15