## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Badkulla Zone-I W/S Scheme in Hanskhali Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000433/2021-2022 | 1053/RSD | 02/12/2021 | 01/01/2022 | RADIANT | 3.29 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1872/ND | 26/04/2023 | 26/04/2023 | Resource Division | 140.17 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BADKULLA (ZONE-I) W/S Scheme, Block- Hanskhali , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 01) |  |  | ORD/000895/2022-2023 | 405/EMD | 20/01/2023 | 19/02/2023 | S.G. ENTERPRISE | 30.45 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
5 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 125 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Badkulla-I to accommodate FHTC within Hanskhali block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000105/2024-2025 | 4281/ND | 05/08/2024 | 01/02/2025 | GHOSH ENTERPRISE | 301.62 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Construction of Jhama Bats Road from Mamjoan road to headwork site of Badkulla-I water supply scheme under Ranaghat Sub Division under Nadia Division P.H. Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000139/2024-2025 | 876(A)RSD | 20/08/2024 | 20/09/2024 | M/S TARAK CHANDRA PAUL | 4.9 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 7556/ND | 27/12/2024 | 27/12/2024 | Resource Division | 4.29 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials and Soil Investigation for Construction of OHR all complete for augmentation of Ground Water Based Water Supply Scheme for Badkulla Zone-I to accommodate FHTC in Hanskhali block under Ranaghat Sub-Division of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000150/2023-2024 | 3217/ND | 26/07/2023 | 01/07/2025 | M/S TARAK CHANDRA PAUL | 676.67 | 0 | 0 | 82
9 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Supplying and laying of distribution system for Augmentation of Ground water based water supply scheme for Badkulla-I to accommodate FHTC under Ranaghat Sub-Division PHED. | Assistant Engineer | Junior Engineer 1 | ORD/000236/2024-2025 | 6502/ND | 03/10/2024 | 31/03/2025 | M/S TARAK CHANDRA PAUL | 87.28 | 0 | 0 | 70
10 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Repairing of Pump house-I with sanitary arrangement under augmentation of Badkulla Zone-I piped water supply scheme under Ranaghat Sub-Division, under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000173/2024-2025 | 1136/RSD | 11/09/2024 | 26/10/2024 | M/S DREAM INFRASTRUCTURE | 1.9 | 0 | 0 | 100
11 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Construction of 130m Boundary Wall(2.5m panel) having 200X200mm R.C.C. Column footing (1.0X1.0m) with 125mm thick brick panel wall and 200x300 RCC beam at GL including M.S gate at Badkulla Zone-I PWSS at H/W site under Ranaghat Sub -Division in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000782/2024-2025 | 458/ND | 29/01/2025 | 29/04/2025 | M/S 2S CONSTRUCTION | 11.35 | 0 | 0 | 75
12 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Construction of R.C.C Elevated Reservoir of 700 Cum. Capacity of staging height 20M at Head works site with Annular combined pile raft foundation for Badkulla Zone-II Water Supply Scheme under Nadia Division P.H.Engineering Dte. | Assistant Engineer |  | ORD/000084/2025-2026 | 2523/ND | 29/05/2025 | 29/05/2026 | SATYABRATA CHAKRABORTY | 164.42 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE | SM/13791 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 1620.28 | 0 | 0