## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer |  | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 17/12/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
2 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Indrakpur water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE DTe. (SM/13820) | Assistant Engineer | Junior Engineer 1 | ORD/000037/2023-2024 | 2104/ND | 15/05/2023 | 14/07/2023 | AUXILIARY TUBEWELL DRILLERS | 32.6 | 24.86 | 76.26 | 70
3 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1854/ND | 26/04/2023 | 26/04/2023 | Resource Division | 15.8 | 0 | 0 | 0
4 | NADIA | Nabadwip | Eastern Mechanical | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Indrakpur ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001987/2023-2024 | 6968/EMD | 15/12/2023 | 15/03/2024 | S.G. TECHNICAL SERVICES | 28.7 | 6.88 | 23.97 | 95
5 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Collection of Household data through mobile app for FHTC Connection of Ground Water Based Indrakpur, Gadigachha, Karimpur-Jalangi (Zone-VI), Sandha, Udaypur PWSS, Mini PWSS at Gazna (Part) and Surface Based PWSS for Northern Sector (Part-I) (Zone-IA) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000338/2023-2024 | 984/KLYSD-I | 11/09/2023 | 10/12/2023 | TECHVISION | 4.85 | 4.85 | 100 | 100
6 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Survey, Design and Preparation of DPR in connection with Indrakpur piped water supply scheme in Nabadwip Block under Krishnanagar Sub Division under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer 1 | ORD/000586/2023-2024 | 49/KSD | 15/01/2024 | 30/01/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 2.79 | 99.17 | 80
7 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 269/ND | 11/01/2024 | 11/01/2024 | Resource Division | 5.7 | 0 | 0 | 0
8 | NADIA | Nabadwip | Eastern Mechanical | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Supplementary quotation for revised estimate due to row issue I.F.O. PHE Dte. for 3PH NSC to pump house-II at Indrakpur |  |  | BILL/01699/2024-2025 | BP-119-24-25 | 20/09/2024 | 20/09/2024 | WBSEDCL NABADWIP CCC | 1.91 | 0 | 0 | 0
9 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000295/2025-2026 | 3784/ND | 12/08/2025 | 12/09/2025 | IMAGIN | 34.21 | 0 | 0 | 0
10 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 m3/hr at Indrakpur Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000295/2024-2025 | 6735/ND | 05/11/2024 | 31/10/2025 | B.M. ENGINEERING & CONSTRUCTION | 159.53 | 0 | 0 | 5
11 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 384.3 | 39.39 | 10.25