## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation of Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub-Division, PHE Dte. for supervision of JJM works for the period 90 days w.e.f. 01/10/2023 (as and when required) | Assistant Engineer |  | ORD/000411/2023-2024 | 1450/KSD | 18/09/2023 | 17/12/2023 | TARUN KUMAR BHATTACHARYA | 1.2 | 0 | 0 | 0
2 | NADIA | Nabadwip | Eastern Mechanical | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Indrakpur ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001987/2023-2024 | 6968/EMD | 15/12/2023 | 15/03/2024 | S.G. TECHNICAL SERVICES | 28.7 | 6.88 | 23.97 | 95
3 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Indrakpur water supply scheme under Krishnagar Sub-Division under Nadia Division, PHE DTe. (SM/13820) | Assistant Engineer | Junior Engineer 1 | ORD/000037/2023-2024 | 2104/ND | 15/05/2023 | 14/07/2023 | AUXILIARY TUBEWELL DRILLERS | 32.6 | 24.86 | 76.26 | 70
4 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Laying of Distribution System including specials & valves, Proposed Laying of Rising Main System, Providing FHTC, Construction of 200 cum capacity R.C.C. Elevated Reservoir including Soil investigation, Construction of Pump House, Boundary Wall and Service Road at Head Work Site & 2nd Tubewell Site at Indrakpur Water Supply Scheme to accommodate FHTC under Krishnagar Sub-Division under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000042/2023-2024 | 1721/ND | 17/04/2023 | 31/12/2024 | M/S GHOSH CONSTRUCTION | 267.51 | 195.02 | 72.9 | 100
5 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Collection of Household data through mobile app for FHTC Connection of Ground Water Based Indrakpur, Gadigachha, Karimpur-Jalangi (Zone-VI), Sandha, Udaypur PWSS, Mini PWSS at Gazna (Part) and Surface Based PWSS for Northern Sector (Part-I) (Zone-IA) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000338/2023-2024 | 984/KLYSD-I | 11/09/2023 | 10/12/2023 | TECHVISION | 4.85 | 4.85 | 100 | 100
6 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 1854/ND | 26/04/2023 | 26/04/2023 | Resource Division | 15.8 | 0 | 0 | 0
7 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 30 m3/hr at Indrakpur Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000295/2024-2025 | 6735/ND | 05/11/2024 | 26/10/2026 | B.M. ENGINEERING & CONSTRUCTION | 159.53 | 0 | 0 | 5
8 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Survey, Design and Preparation of DPR in connection with Indrakpur piped water supply scheme in Nabadwip Block under Krishnanagar Sub Division under Nadia Division, PHE Dte | Assistant Engineer | Junior Engineer 1 | ORD/000586/2023-2024 | 49/KSD | 15/01/2024 | 30/01/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.82 | 2.79 | 99.17 | 80
9 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Providing FHTC at leftout in connection to the Ground Based Piped Water Supply Scheme at Indrakpur to accomodate FHTC within Nabadwip Block under Krishnagar Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000771/2023-2024 | 1761/ND | 12/03/2024 | 08/12/2024 | M/S GHOSH CONSTRUCTION | 12.79 | 12.34 | 96.53 | 100
10 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 269/ND | 11/01/2024 | 11/01/2024 | Resource Division | 5.7 | 0 | 0 | 0
11 | NADIA | Nabadwip | Eastern Mechanical | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Supplementary quotation for revised estimate due to row issue I.F.O. PHE Dte. for 3PH NSC to pump house-II at Indrakpur |  |  | BILL/01699/2024-2025 | BP-119-24-25 | 20/09/2024 | 20/09/2024 | WBSEDCL NABADWIP CCC | 1.91 | 0 | 0 | 0
12 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000295/2025-2026 | 3784/ND | 12/08/2025 | 12/09/2025 | IMAGIN | 34.21 | 0 | 0 | 0
13 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
14 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000109/2025-2026 | 2229/ND | 13/05/2025 | 27/06/2025 | IMAGIN | 19.44 | 0 | 0 | 100
15 | NADIA | Nabadwip | Nadia Division | Indrakpur Piped Water Supply Scheme. | SM/13820 | New | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000895/2024-2025 | 1346/ND | 20/03/2025 | 04/05/2025 | IMAGIN | 19.44 | 0 | 0 | 100
Total | [13 empty] | 703.47 | 246.75 | 35.08