## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Fulia Township (Zone-III) Water Supply Scheme in Santipur Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000044/2023-2024 | 423/RSD | 08/05/2023 | 23/05/2023 | HORIZEN | 2.7 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1885/ND | 26/04/2023 | 26/04/2023 | Resource Division | 7.4 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
4 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Providing, installation and commissioning of Electro-Mechanical Equipments and allied works for submersible pumping machinery of Pump House No.-I and II (New) for Augumentation Tube Well and Arsenic Removal Plant in connection to Accommodate FHTC under Fulia Town Ship (Zone-III) ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-13878] | Assistant Engineer |  | ORD/000342/2024-2025 | 2157/EMD | 30/08/2024 | 29/09/2024 | PADMA ENGINEERING CO. | 26.83 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Construction of Arsenic-Cum- Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-III to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000096/2024-2025 | 4231/ND | 02/08/2024 | 29/01/2025 | SATYABRATA CHAKRABORTY | 160.53 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | New power connection charges for FULIA Water Supply scheme Z-III , Pump House NO-I (HEAD WORKSITE) |  |  | BILL/02291/2024-2025 | BP-184 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (FULIA C.C.C) | 9.47 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Augmentation of Ground Water Based Piped Water Supply Scheme to Accommodate FHTC, Construction & Soil Investigation of 100 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection and Cost of Pipes, Specials for FULIA Zone-III of Nadia District under Nadia Division PHE Dte | Assistant Engineer | Junior Engineer 2 | ORD/000160/2023-2024 | 3222/ND | 26/07/2023 | 26/07/2026 | SANJOY BAKSHI, 11,AHIBHUSAN HALDER LANE, SASTITALA.PO-KRISHNAGAR,DIST-NADIA, PIN-741101 | 237.03 | 0 | 0 | 51
8 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Construction of 137.00 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125 mm thick brick panel wall and 200x300 m tie beam at GL including M.S gate at Fulia Zone-III H/W under Ranaghat Sub-Div , Nadia Division PHE. Dte. | Assistant Engineer |  | ORD/000771/2024-2025 | 658/ND | 11/02/2025 | 12/05/2025 | MUKHERJEE CONSTRUCTION | 11.66 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Head work Site At Fulia Zone-III Water Supply Scheme Under Ranaghat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000775/2024-2025 | 662/ND | 11/02/2025 | 12/05/2025 | ABHAYANANDA ENTERPRISE | 6.88 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
11 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/13878 | Augmentation | Providing clriiling crew and other allied rvorks for constructioti of Tube Well (300mm X200rnrr X 250 Mtrs. Depth) by utilising Depaftmental Machineries for Fulia Township W/S Scheme (Z- lll, T/W-l),santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000095/2023-2024 | 514/CDD | 01/06/2023 | 01/02/2025 | S B S ENTERPRISE | 18.88 | 0 | 0 | 100
Total | [13 empty] | 675.31 | 0 | 0