## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Route Survey, Design of Distribution Network and Preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapno for Anjangarh Water Supply Scheme in Ranaghat-I Block of Nadia District under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000043/2023-2024 | 424/RSD | 08/05/2023 | 23/05/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.45 | 2.45 | 99.72 | 0
2 | NADIA | Ranaghat-I | Central Drilling | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR ANJANGARH W/S SCHEME (TW-I & II), RANAGHAT-I BLOCK UNDER NADIA DISTRICT, CDD, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 1230/CDD | 04/09/2023 | 04/10/2023 | MENAKA ENTERPRISE | 37.76 | 29.02 | 76.86 | 100
3 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1871/ND | 26/04/2023 | 26/04/2023 | Resource Division | 11.91 | 0 | 0 | 0
4 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 2586/ND | 13/06/2023 | 13/06/2023 | Resource Division | 11.91 | 0 | 0 | 0
5 | NADIA | Ranaghat-I | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Anjangarh Piped Water Supply Scheme Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. 2024_PHED_664112_3 | Assistant Engineer |  | ORD/003003/2023-2024 | 925/EMD | 15/03/2024 | 14/04/2024 | DEY ENTERPRISE | 42.34 | 0 | 0 | 0
6 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 30 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Anjangarh to accommodate FHTC within Ranaghat-I block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000080/2024-2025 | 4126/ND | 29/07/2024 | 25/01/2025 | G.D. CONSTRUCTION AND CO. | 161.1 | 0 | 0 | 0
7 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 272/ND | 11/01/2024 | 11/01/2024 | Resource Division | 3.55 | 0 | 0 | 0
8 | NADIA | Ranaghat-I | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | New Service connection Charges for ANJANGARH Piped Water supply scheme PUMP House No- II |  |  | BILL/00608/2024-2025 | BP-37-24-25 | 31/05/2024 | 31/05/2024 | WBSEDCL BADKULLA CCC | 3.8 | 0 | 0 | 0
9 | NADIA | Ranaghat-I | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | NEW SERVICE CONNECTION CHARGES FOR ANJANGARH PWSS PH-I (HEAD WORK SITE) |  |  | BILL/00737/2024-2025 | BP-52-24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL BADKULLA CCC | 7.88 | 0 | 0 | 0
10 | NADIA | Ranaghat-I | Eastern Mechanical | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Anjangarh ground water based water supply scheme under Block_ Ranaghat-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002814/2023-2024 | 803/EMD | 11/03/2024 | 29/06/2025 | S.G. ENTERPRISE | 25.38 | 0 | 0 | 85
11 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc., Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir, pipe connection and cost of pipes, specials SOIL INVESTIGATION FOR CONSTRUCTION OF OHR all complete for Ground Water Based Water Supply Scheme for Anjangarh to accommodate FHTC in Ranaghat-I block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000448/2022-2023 | 963/ND | 09/03/2023 | 01/06/2025 | M/S BISWAS BROTHERS, VIVEKNAGAR, P.O-NOAPARA, P.S-BARASAT, KOLKATA-700125 | 135.42 | 78.87 | 58.24 | 95
12 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Augmentation of Ground Water Based Piped Water Supply Scheme forAnjangarh Water Supply scheme under Ranaghat Block in Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000401/2023-2024 | 5210/ND | 23/11/2023 | 15/02/2025 | M/S A.K.CONSTRUCTION | 26.37 | 12.77 | 48.43 | 95
13 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Area development at Anjangarh W/S Scheme under Ranaghat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000127/2024-2025 | 767(C)RSD | 23/07/2024 | 21/09/2024 | ANJALI ENTERPRISE | 3 | 2.98 | 99.55 | 100
14 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Tube well No-2 site at Anjangarh Water supply scheme under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000125/2024-2025 | 767(B)RSD | 23/07/2024 | 21/09/2024 | ANJALI ENTERPRISE | 4.24 | 0.05 | 1.13 | 100
15 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Construction of Boundary wall at Tube well No-2 site at Anjangarh Ground water based water supply scheme under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000124/2024-2025 | 767/A/RSD | 23/07/2024 | 06/09/2024 | ANJALI ENTERPRISE | 4.61 | 0 | 0 | 100
16 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000109/2025-2026 | 2229/ND | 13/05/2025 | 27/06/2025 | IMAGIN | 19.44 | 0 | 0 | 100
17 | NADIA | Ranaghat-I | Nadia Division | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District | SM/14063 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000295/2025-2026 | 3784/ND | 12/08/2025 | 12/09/2025 | IMAGIN | 34.21 | 0 | 0 | 0
Total | [13 empty] | 535.36 | 126.14 | 23.56