## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | SUPPLY, COMMISSIONING & MONITORING OF INTELLIGENT DISINFECTION SYSTEMS FOR FREE COMPLETE DISINFECTION OF DRINKING WATER SUPPLIED THROUGH PIPED WATER SUPPLY SCHEMES WITH MONITORING OF DOSAGE STRENGTH FOR ADDITIONAL 4 NOS AT BARAKULTA WATER SUPPLY SCHEME UN | SM/14142 | Support-WQMSP | Supply , Commissioning & Monitoring of Intelligent Disinfection systems for free complete disinfection of drinking water supplied through piped water supply schemes with monitoring of dosage strength for 5 nos at Barakulta water supply scheme under Nadia Division ,P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000323/2022-2023 | 66/ND | 05/01/2023 | 05/04/2023 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 12.58 | 9.84 | 78.2 | 70
Total | [13 empty] | 12.58 | 9.84 | 78.2